## Pre-Hearing
PRE-HEARING DESIGN REVIEW CHECKLIST
[6 empty] | Version Date: | 2024-10-08 | Initials should be person who did the check.
PROJECT: | [7 empty] | The checker should be experienced.
ID |  | ITEM | DONE | DATE | CHECKED | DATE | REMARKS | NARRATIVE
|  |  | BY |  | BY
In many cases for this submission, work would have been done during Preliminary Design. In this case, required information below may need to be revised as a result of Public Hearing comments, verified or updated.
PHDR - | 1 | REQUIRED SUBMISSION ITEMS
PHDR - | 1.1 | Plans
PHDR - | 1.2 | Design Report | [5 empty] | All preliminary design sections addressed prior to Hearing
PHDR - | 2 | REQUIRED DESIGN CHECKS
PHDR - | 2.1 | Vertical curve vs. horizontal curve placement. | [5 empty] | Generally included in Design Report. Justify if not met.
PHDR - | 2.2 | K values vs. Green Book standards. | [5 empty] | Generally included in Design Report. Justify if not met.
PHDR - | 2.3 | Minimum/maximum grades vs. Green Book standards | [5 empty] | Generally included in Design Report. Justify if not met.
PHDR - | 2.4 | Turning lanes and intersections designed per Design Manual sample layouts. | [5 empty] | Turning lane lengths based on storage and decel requirements.
PHDR - | 2.5 | Critical turning movements at all side roads and major intersections. | [5 empty] | CADD deliverable available on request. Hard copy printouts available if stipulated in the scope
PHDR - | 2.6 | Intersection, passing, stopping sight distances. | [5 empty] | Generally included in Design Report. Justify if not met.
PHDR - | 2.7 | Verify project begins and ends in a convenient and logical location.
PHDR - | 2.8 | Verify confidence in property impacts shown for Hearing Plan | [5 empty] | NHDOT to craft memo with language from ROW
PHDR - | 2.9 | Identify Constructability Issues | [5 empty] | Check to ensure project can be built within proposed ROW/easements. Identify issues for future resolution
PHDR - | 2.1 | Roadside hazards identified
PHDR - | 2.11 | Verify cross section template is consistent with typical sections
PHDR - | 2.12 | Verify superelevation transitions | [5 empty] | Check for transition rates in reverse / broken back curves, transitions in low points, proper e-max
PHDR - | 3 | PLANS
PHDR - | 3.1 | TYPICAL SECTIONS | [5 empty] | Minimum information should include; lane and shoulder width, curb section, sidewalk width, ditch width, and ledge cut typical.
PHDR - | 3.2 | GENERAL PLANS | [5 empty] | Roll plans or cut sheets may be acceptable
PHDR - | 3.2.1 | EXISTING INFORMATION
PHDR - | 3.2.1.1 | Drafted at scale per agreement
PHDR - | 3.2.1.2 | Existing ground detail
PHDR - | 3.2.1.3 | Existing utilities
PHDR - | 3.2.1.4 | Existing environmental information (i.e. wetland delineation)
PHDR - | 3.2.1.5 | Existing ROW information (ROW lines, property lines, etc.)
PHDR - | 3.2.1.6 | Existing drainage
PHDR - | 3.2.2 | PROPOSED INFORMATION
PHDR - | 3.2.2.1 | Complete conceptual alignments and curve data
PHDR - | 3.2.2.2 | Match alignments back to existing in the center of the road.
PHDR - | 3.2.2.3 | Label travel lane widths | [5 empty] | Once per page and areas of change
PHDR - | 3.2.2.4 | Label taper rates | [5 empty] | Taper rates can be labeled on the line tapering. Start and end taper locations are not required at this phase.
PHDR - | 3.2.2.5 | Label drive widths.
PHDR - | 3.2.2.6 | Show major features | [5 empty] | Culverts, bridges, pedestrian/snowmobile crossings, major outfalls, and BMPs
PHDR - | 3.2.2.7 | Show proposed retaining walls
PHDR - | 3.2.2.8 | Show proposed drainage
PHDR - | 3.3 | PROFILES | [5 empty] | Roll plans or cut sheets may be acceptable
PHDR - | 3.3.1 | Label vertical curve information | [5 empty] | VPT, VPI, VPC, low points, high points, K values, etc.
PHDR - | 3.3.3 | Match profile into existing road profile at begin and end in a convenient and logical location
PHDR - | 3.3.5 | Side road profiles | [5 empty] | Includes appropriate platform intersecting main alignment
PHDR - | 3.4 | CONCEPTUAL TRAFFIC CONTROL PLANS | [5 empty] | The scope of work should detail what items will be required at this stage of the project. If full TCP plans are anticipated, then all the items in this list may be appropriate. Submittal requirement will depend on the project complexity and should be clearly detailed in the scope of work. In most cases this can be a narrative with critical sections.
PHDR - | 3.4.1 | Conceptual TCP typical section
PHDR - | 3.4.2 | Initial TCP alignments and curve data
PHDR - | 3.4.3 | Label lane widths
PHDR - | 3.4.4 | Label taper rates
PHDR - | 3.4.5 | Show phasing for major design features | [5 empty] | Deep pipes, bridges, significant profile changes, etc.
PHDR - | 3.4.6 | Show phasing for major intersection work | [5 empty] | Traffic signals, roundabouts, etc.
PHDR - | 3.4.7 | Critical phasing cross sections | [5 empty] | Discuss number of potential sections at scoping
PHDR - | 3.4.8 | Diversion cross sections | [5 empty] | Discuss number of potential sections at scoping
PHDR - | 3.5 | CROSS SECTIONS | [5 empty] | Presentation of these working cross sections should be as produced by OpenRoads with little to no manual editing for presentation.
PHDR - | 3.5.1 | Show top line of template
PHDR - | 3.5.2 | Show proposed retaining walls
PHDR - | 3.5.3 | Show proposed drainage
PHDR - | 3.5.5 | Show existing utilities. Include proposed if known
PHDR - | 3.5.6 | Show environmental boundaries (wetlands, etc.)
PHDR - | 3.5.7 | Show ROW information
PHDR - | 3.5.8 | Label existing and proposed profile elevations
PHDR - | 3.5.9 | Label superelevations. | [5 empty] | Frequency as presented by OpenRoads
PHDR - | 3.5.10 | Label side slopes
PHDR - | 3.511 | Include sections at all critical sections. | [5 empty] | Use judgment on when skewed sections are needed. Should generally match side road profile.
PHDR - | 3.5.12 | Include sections at all major drive locations. | [5 empty] | Use judgment on when skewed sections are needed
PHDR - | 3.5.13 | Include sections at major drainage locations / culverts | [5 empty] | Use judgment on when skewed sections are needed...PMs can change the frequency during the scoping process
PHDR - | 4 | DESIGN REPORT INFORMATION - ALL PRELIMINARY DESIGN SECTIONS
PHDR - | 4.1 | Narrative | [5 empty] | Include project description, existing deficiencies, design solutions, typical section used, any design assumptions, maintenance/operations issues, etc.
PHDR - | 4.2 | Updated Design Criteria Form
PHDR - | 4.3 | Final Report Outline and Memo | [5 empty] | Signal warrants Left and Right Turn Lane Warrants LOS Calculations Queue Length Calculations Turning Lane Storage / Length Calculations Segment Capacity Signal Coordination Analysis
PHDR - | 4.4 | Pedestrian & Bicycle Accommodations
PHDR - | 4.5 | Superelevation Calculations | [5 empty] | This can be openroads generated reports showing the emax and superelevation transitions. Detailed superelevation transition calculations will be finalized at the Line and Grade submission.
PHDR - | 4.6 | Traffic Control Narrative | [5 empty] | Include discussion on temporary bicycle & pedestrian accommodations
PHDR - | 4.7 | Construction Schedule | [5 empty] | High level to determine project duration.
PHDR - | 4.8 | Geotechnical Issues
PHDR - | 4.9 | Environmental | [5 empty] | -Generate a list of environmental commitments with updates in matrix form. This will be a living document through the design phase. -list Purpose & Need statement for project
PHDR - | 4.1 | Preliminary Drainage | [5 empty] | -Figures showing existing and proposed watersheds for each outlet location -Potential outlets described with pre-development vs. post-development flow rates -MS4 and AoT treatment requirements identified -BMP locations and types identified -Erosion and outlet protection identified
PHDR - | 4.11 | Utility Issues/Concerns | [5 empty] | Generally describe which utilities are impacted with locations and why impacts couldn't be avoided.
PHDR - | 4.12 | Study estimate | [5 empty] | Should be an updated version of the Pre-Hearing estimate, check high cost items and various percentages for appropriate values.
PHDR - | 4.13 | Any Pending/Outstanding Issues | [5 empty] | Has any issues that has not been addressed, need DOT input, or additional information been identified by the Consultant. Anything that could cause future delays.

## Line & Grade
LINE AND GRADE DESIGN REVIEW CHECKLIST
[6 empty] | Version Date: | 2024-10-08 | Initials should be person who did the check.
PROJECT: | [7 empty] | The checker should be experienced.
ID |  | ITEM | DONE | DATE | CHECKED | DATE | REMARKS | NARRATIVE
|  |  | BY |  | BY
LGDR | 1 | REQUIRED SUBMISSION ITEMS
LGDR | 1.1 | Plans
LGDR | 1.2 | Design Report
LGDR | 1.3 | Drainage Report
LGDR | 2 | REQUIRED DESIGN CHECKS
LGDR | 2.1 | Verify all comments from Post-Hearing Design Review Submission have been addressed.
LGDR | 2.2 | Vertical Curve vs. horizontal curve placement | [5 empty] | Generally included in Design Report. Justify if not met.
LGDR | 2.3 | K values vs. Green Book standards | [5 empty] | Generally included in Design Report. Justify if not met.
LGDR | 2.4 | Minimum/maximum grades vs. Green Book standards | [5 empty] | Generally included in Design Report. Justify if not met.
LGDR | 2.5 | Turning lanes and intersections designs per Design Manual sample layouts
LGDR | 2.6 | Turn lanes, ramp lengths, etc. match traffic analysis | [5 empty] | Lengths based on storage and decel requirements
LGDR | 2.7 | Turning movements at all side roads and commercial driveways | [5 empty] | CADD deliverable available on request. Hard copy printouts available if stipulated in the scope
LGDR | 2.8 | Intersection, passing, and stopping sight distances | [5 empty] | Generally included in Design Report. Justify if not met.
LGDR | 2.9 | Verify project begins and ends in a convenient and logical location
LGDR | 2.1 | Verify property impacts are withing ROW or easements
LGDR | 2.11 | Intersection and ramp nose grading (show contours developed by model) | [5 empty] | CADD deliverable of top line contours available upon request. Hard copy printouts available if stipulated in the scope
LGDR | 2.12 | Headlight Glare Screens | [5 empty] | CADD deliverable available upon request. Hard copy printouts available if stipulated in the scope
LGDR | 2.13 | Edge line profiles in superelevation transitions (show contours developed by model) | [5 empty] | CADD deliverable of top line contours and digital terrain available upon request. Hard copy printouts available if stipulated in the scope
LGDR | 3 | PLANS
LGDR | 3.1 | TYPICAL SECTIONS
LGDR | 3.1.1 | Provide Typical Section for Each Roadway
LGDR | 3.1.2 | Normal Crown Section
LGDR | 3.1.3 | Superelevation Section (If Needed)
LGDR | 3.1.4 | Sidewalks
LGDR | 3.1.5 | Raised Islands
LGDR | 3.1.6 | Show Crown Line Location
LGDR | 3.1.7 | Show Profile Grade Line Location (Interstate Projects)
LGDR | 3.1.8 | Sound Walls
LGDR | 3.1.9 | Retaining Walls
LGDR | 3.1.10 | Lane and Shoulder Widths
LGDR | 3.1.11 | Cross Slopes
LGDR | 3.1.12 | Pavement Type and Thickness
LGDR | 3.1.13 | Subbase Types and Thicknesses
LGDR | 3.1.14 | Underdrain Location
LGDR | 3.1.15 | Guardrail Offset
LGDR | 3.1.16 | Median Barrier
LGDR | 3.1.17 | Curb Type
LGDR | 3.1.18 | Sideslope Treatment
LGDR | 3.2 | TRAFFIC CONTROL TYPICAL SECTIONS
LGDR | 3.2.1 | Provide Typical Section for Each Phase of Construction
LGDR | 3.2.2 | Show Alignment Location
LGDR | 3.2.3 | Lane and Shoulder Widths
LGDR | 3.2.4 | Cross Slopes
LGDR | 3.2.5 | Pavement Type and Thickness
LGDR | 3.2.6 | Subbase Types and Thicknesses
LGDR | 3.2.7 | Portable Concrete Barrier Location
LGDR | 3.2.8 | Sideslope Treatment
LGDR | 3.3 | GENERAL PLANS | [5 empty] | Roll plans are required with anticipated sheet limits shown on the general plan
LGDR | 3.3.1 | EXISTING INFORMATION | [5 empty] | No rotation of labels to match sheet orientation needed for this submission
LGDR | 3.3.2 | Drafted at scale per agreement
LGDR | 3.3.3 | City/Town lines
LGDR | 3.3.4 | Existing ground detail
LGDR | 3.3.5 | Existing utilities
LGDR | 3.3.6 | Existing environmental information
LGDR | 3.3.7 | Wetland delineation
LGDR | 3.3.8 | Invasive Species
LGDR | 3.3.9 | Ordinary High Water
LGDR | 3.3.10 | Existing ROW Information
LGDR | 3.3.11 | ROW Lines with ROW Type Labels
LGDR | 3.3.12 | Property Lines
LGDR | 3.3.13 | Property Owner Names
LGDR
LGDR | 3.3.2 | PROPOSED INFORMATION
LGDR | 3.3.3 | Alignment with stationing
LGDR | 3.3.4 | Curves labeled with curve data
LGDR | 3.3.5 | Match Alignments back to existing in the center of the road
LGDR | 3.3.6 | Show intersection equations
LGDR | 3.3.7 | Label travel lane widths | [5 empty] | Once per sheet and at transition points
LGDR | 3.3.8 | Label taper rates
LGDR | 3.3.9 | Label drive widths
LGDR | 3.3.10 | Show major features
LGDR | 3.3.11 | Show proposed retaining walls and sound walls
LGDR | 3.3.12 | Show preliminary closed drainage system | [5 empty] | General layout of system to be included with generic catch basin layout. Critical inlets at low points, superelevation rollovers, etc. should be shown with estimated spacing in other locations. Pipe layout shown but pipe sizing calculations not required.
LGDR | 3.3.13 | Show underdrain locations
LGDR | 3.3.14 | Show proposed best management practices (BMPs) | [5 empty] | BMP locations and types identified and NHDES worksheets completed for each BMP
LGDR | 3.3.15 | Show cut and fill lines (rounded) and clearing line
LGDR | 3.3.16 | Show proposed ROW lines and permanent easements
LGDR | 3.3.17 | Show crosswalk locations
LGDR | 3.3.18 | Show traffic signal equipment
LGDR | 3.4 | PROFILES
LGDR | 3.4.1 | Label vertical curve information (grades, VPT, VPI, VPC, K-values, low points, etc.)
LGDR | 3.4.2 | Show superelevation transitions
LGDR | 3.4.3 | Intersection road equations
LGDR | 3.4.4 | Match profile into existing road profile at begin and end in a convenient and logical location
LGDR | 3.4.5 | Include side road profiles
LGDR | 3.4.6 | Include BMP profiles
LGDR | 3.4.7 | Show bridges and large culverts
LGDR | 3.4.8 | Show matches from existing pavement to proposed pavement
LGDR | 3.4.9 | Show railroad crossings
LGDR | 3.5 | TRAFFIC CONTROL PLANS
LGDR | 3.5.1 | Alignment with stationing
LGDR | 3.5.2 | Curves labeled with curve data
LGDR | 3.5.3 | Label travel lane widths
LGDR | 3.5.4 | Label taper rates
LGDR | 3.5.5 | Show phasing for major design features
LGDR | 3.5.6 | Show proposed retaining walls and sound walls
LGDR | 3.5.7 | Show preliminary temporary closed drainage system | [5 empty] | General layout of system to be included with generic catch basin layout. Critical inlets at low points, superelevation rollovers, etc. should be shown with estimated spacing in other locations. Pipe layout shown but pipe sizing calculations not required.
LGDR | 3.5.8 | Show temporary cut and fill lines
LGDR | 3.5.9 | Show proposed ROW lines and permanent easements
LGDR | 3.5.10 | Shade area of construction
LGDR | 3.5.11 | Show Existing Condition Detail in Grayscale
LGDR | 3.5.12 | Show temporary bridges
LGDR | 3.5.13 | Show staging areas
LGDR | 3.5.14 | Show construction access
LGDR | 3.5.15 | Show Pedestrian Route
LGDR | 3.6 | TRAFFIC CONTROL PROFILES
LGDR | 3.6.1 | Provide for all diversions
LGDR | 3.6.2 | Label vertical curve information (grades, VPT, VPI, VPC, K-values, low points, etc.)
LGDR | 3.6.3 | Show superelevation transitions
LGDR | 3.6.4 | Intersection road equations
LGDR | 3.6.5 | Match profile into existing road profile at begin and end in a convenient and logical location
LGDR | 3.6.6 | Include side road profiles
LGDR | 3.6.7 | Include BMP profiles
LGDR | 3.6.8 | Show bridges and large culverts
LGDR | 3.6.9 | Show matches from existing pavement to proposed pavement
LGDR | 3.7 | FINAL CROSS SECTIONS | [5 empty] | Presentation of these sections should be as produced by OpenRoads with little to no manual editing for presentation.
LGDR | 3.7.1 | Include sections at all control points along the design
LGDR | 3.7.2 | Include sections at all side road intersections
LGDR | 3.7.3 | Include sections at all drive locations
LGDR | 3.7.4 | Include sections at major drainage locations/culverts
LGDR | 3.7.5 | Include sections at BMPs
LGDR | 3.7.6 | Include sections at Limit of Work
LGDR | 3.7.7 | Include sections at Overhead Sign Structures
LGDR | 3.7.8 | Show top line of proposed template and bottom of subgrade
LGDR | 3.7.9 | Label existing and proposed profile elevations
LGDR | 3.7.10 | Label superelevations | [5 empty] | As annotated by OpenRoads. Some text overlap expected.
LGDR | 3.7.11 | Label side slopes | [5 empty] | As annotated by OpenRoads. Some text overlap expected.
LGDR | 3.7.12 | Show slope tick marks
LGDR | 3.7.13 | Show surfaces of adjacent roadways
LGDR | 3.7.14 | Show guardrail | [5 empty] | Don't need to show platform grading at this submission.
LGDR | 3.7.15 | Show existing features including underground utilities and drainage
LGDR | 3.8 | TRAFFIC CONTROL CROSS SECTIONS | [5 empty] | Presentation of these sections should be as produced by OpenRoads with little to manual editing for presentation. Sections showing temporary widening are considered critical in addition to other critical locations.
LGDR | 3.8.1 | Include sections for each phase of construction
LGDR | 3.8.2 | Include sections at all side road intersections
LGDR | 3.8.3 | Include sections at all drive locations
LGDR | 3.8.4 | Include sections at major drainage locations/culverts
LGDR | 3.8.5 | Show top line of proposed template and bottom of subgrade
LGDR | 3.8.6 | Label existing and proposed profile elevations
LGDR | 3.8.7 | Label superelevations
LGDR | 3.8.8 | Label side slopes
LGDR | 3.8.9 | Show surfaces of previously constructed work
LGDR | 3.8.10 | Show portable concrete barrier
LGDR | 3.8.11 | Show existing features including underground utilities and drainage
LGDR | 3.8.12 | Label work zone area and where traffic is being maintained
LGDR | 3.8.13 | Show temporary excavation supports
LGDR | 4 | DESIGN REPORT INFORMATION | [5 empty] | See Sample Engineering Report
LGDR | 4.1 | Narrative
LGDR | 4.2 | Updated Design Criteria Form
LGDR | 4.3 | Finalized Traffic Analysis | [5 empty] | Updated from previous submission
LGDR | 4.4 | Including Temporary Conditions
LGDR | 4.5 | Pedestrian and Bicycle Accommodations
LGDR | 4.6 | Superelevation Calculations | [5 empty] | Detailed superelevation transition calculations required
LGDR | 4.7 | Guardrail Calculations | [5 empty] | Detailed guardrail calculations required
LGDR | 4.8 | Vertical Clearance Calculations
LGDR | 4.9 | Acceleration/Deceleration/Storage Length Calculations
LGDR | 4.1 | Traffic Control Narrative
LGDR | 4.11 | Construction Schedule | [5 empty] | High level to determine project duration
LGDR | 4.12 | Geotechnical Report
LGDR | 4.13 | Engineering Report
LGDR | 4.14 | Environmental | [5 empty] | Provide updates on Environmental Commitments
LGDR | 4.15 | Utility Issues/Concerns | [5 empty] | Generally describe which utilities are impacted and why impacts couldn't be avoided
LGDR | 4.16 | Utility Pole Relocation Sheet (Existing Poles Only)
LGDR | 4.17 | List of Potential Utility Conflicts (Listed by Utility) | [5 empty] | List of utility impact with Station/Offset locations
LGDR | 4.18 | Estimate | [5 empty] | More detail and samples coming from DOT
LGDR | 4.19 | Pending/Outstanding Issues | [5 empty] | Have any issues that have not been addressed need DOT input or has the need for additional information been identified by the Consultant. Anything that could cause future delays should be highlighted
LGDR | 5 | DRAINAGE REPORT INFORMATION
LGDR | 5.1 | Narrative
LGDR | 5.2 | Pre-Development flows calculated at every outlet location
LGDR | 5.3 | Post-Development flows calculated at every outlet location
LGDR | 5.4 | Preliminary BMP type selected and preliminarily sized
LGDR | 5.5 | NHDES BMP Worksheets Completed
LGDR | 5.6 | Infiltration testing and groundwater elevation needs identified
LGDR | 5.7 | Stormwater Treatment Summary
LGDR | 5.8 | Large Culvert Analysis | [5 empty] | Tier 2 & Tier 3 Crossings

## Post Hearing
POST-HEARING DESIGN REVIEW CHECKLIST
[6 empty] | Version Date: | 2024-10-08 | Initials should be person who did the check.
PROJECT: | [7 empty] | The checker should be experienced.
ID |  | ITEM | DONE | DATE | CHECKED | DATE | REMARKS | NARRATIVE
|  |  | BY |  | BY
AHDR - | 1 | REQUIRED SUBMISSION ITEMS | [5 empty] | In many cases for this submission, work would have been done during preliminary design. In this case, required information below may need to be revised as a result of public hearing comments, verified or updated.
PHDR - | 1.1 | Plans
PHDR - | 1.2 | Design Report
PHDR - | 2 | REQUIRED DESIGN CHECKS
PHDR - | 2.1 | Vertical curve vs. horizontal curve placement. | [5 empty] | Generally included in Design Report. Justify if not met.
PHDR - | 2.2 | K values vs. Green Book standards. | [5 empty] | Generally included in Design Report. Justify if not met.
PHDR - | 2.3 | Minimum/maximum grades vs. Green Book standards | [5 empty] | Generally included in Design Report. Justify if not met.
PHDR - | 2.4 | Turning lanes and intersections designed per Design Manual sample layouts. | [5 empty] | Turning lane lengths based on storage and decel requirements.
PHDR - | 2.5 | Critical turning movements at all side roads and major intersections. | [5 empty] | CADD deliverable available on request. Hard copy printouts available if stipulated in the scope
PHDR - | 2.6 | Intersection, passing, stopping sight distances. | [5 empty] | Generally included in Design Report. Justify if not met.
PHDR - | 2.7 | Verify project begins and ends in a convenient and logical location.
PHDR - | 2.8 | Verify property impacts are consistent with those shown on the Hearing Plan.
PHDR - | 2.9 | Verify design vs. Hearing Plan for various design aspects | [5 empty] | Ensure their incorporation (i.e. walkway matches, easements, property impacts, etc.)
Verify that the Report of the Commissioner commitments been incorporated.
PHDR - | 2.1 | Identify Constructability Issues | [5 empty] | Check to ensure project can be built within proposed ROW/easements.
Identify issues for future resolution
PHDR - | 2.11 | Verify cross section template is consistent with typical sections
PHDR - | 2.12 | Superelevation transitions | [5 empty] | Check for transition rates in reverse / broken back curves, transitions in low points, proper e-max
PHDR - | 3 | PLANS
PHDR - | 3.1 | TYPICAL SECTIONS | [5 empty] | Minimum information should include; lane and shoulder width, curb section, sidewalk width, ditch width, and ledge cut typical.
PHDR - | 3.2 | GENERAL PLANS | [5 empty] | Roll plans or cut sheets may be acceptable
PHDR - | 3.2.1 | EXISTING INFORMATION
PHDR - | 3.2.1.1 | Drafted at scale per agreement
PHDR - | 3.2.1.2 | Existing ground detail
PHDR - | 3.2.1.3 | Existing utilities
PHDR - | 3.2.1.4 | Existing environmental information (i.e. wetland delineation)
PHDR - | 3.2.1.5 | Existing ROW information (ROW lines, property lines, etc.)
PHDR - | 3.2.2 | PROPOSED INFORMATION
PHDR - | 3.2.2.1 | Complete conceptual alignments and curve data
PHDR - | 3.2.2.2 | Match alignments back to existing in the center of the road.
PHDR - | 3.2.2.3 | Label travel lane widths | [5 empty] | Once per page
PHDR - | 3.2.2.4 | Label taper rates | [5 empty] | Taper rates can be labeled on the line tapering. Start and end taper locations are not required at this phase.
PHDR - | 3.2.2.5 | Label drive widths.
PHDR - | 3.2.2.6 | Show major features | [5 empty] | Culverts, bridges, pedestrian/snowmobile crossings, major outfalls, and BMPs
PHDR - | 3.2.2.7 | Show proposed retaining walls
PHDR - | 3.3 | PROFILES | [5 empty] | Roll plans or cut sheets may be acceptable
PHDR - | 3.3.1 | Label vertical curve information | [5 empty] | VPT, VPI, VPC, low points, high points, K values, etc.
PHDR - | 3.3.2 | Show superelevation transitions
PHDR - | 3.3.3 | Match profile into existing road profile at begin and end in a convenient and logical location
PHDR - | 3.3.4 | Intersecting road equations
PHDR - | 3.3.5 | Side road profiles | [5 empty] | Includes appropriate platform intersecting main alignment
PHDR - | 3.4 | CONCEPTUAL TRAFFIC CONTROL PLANS | [5 empty] | The scope of work should detail what items will be required at this stage of the project. If full TCP plans are anticipated, then all the items in this list may be appropriate. Submittal requirement will depend on the project complexity and should be clearly detailed in the scope of work. In most cases this can be a narrative with critical sections.
PHDR - | 3.4.1
PHDR - | 3.4.2 | Conceptual TCP alignments and curve data
PHDR - | 3.4.3 | Label lane widths
PHDR - | 3.4.4 | Label taper rates
PHDR - | 3.4.5 | Show phasing for major design features | [5 empty] | Deep pipes, bridges, significant profile changes, etc.
PHDR - | 3.4.6 | Show phasing for major intersection work | [5 empty] | Traffic signals, roundabouts, etc.
PHDR - | 3.4.7 | Critical phasing cross sections
PHDR - | 3.5 | CROSS SECTIONS | [5 empty] | Presentation of these working cross sections should be as produced by OpenRoads with little to no manual editing for presentation.
PHDR - | 3.5.1 | Show top line of template
PHDR - | 3.5.2 | Label existing and proposed profile elevations
PHDR - | 3.5.3 | Label superelevations | [5 empty] | Frequency as presented by OpenRoads
PHDR - | 3.5.4 | Label side slopes
PHDR - | 3.5.5 | Include sections included at all control points along the design | [5 empty] | Define "control point"
PHDR - | 3.5.6 | Include sections included at all side road intersections | [5 empty] | Use judgment on when skewed sections are needed. Should generally match side road profile.
PHDR - | 3.5.7 | Include sections included at all major drive locations | [5 empty] | Use judgment on when skewed sections are needed
PHDR - | 3.5.8 | Include sections included at major drainage locations / culverts | [5 empty] | Use judgment on when skewed sections are needed
PHDR - | 3.5.9 | Show proposed retaining walls
PHDR - | 3.5.10 | Existing Utilities
PHDR - | 4 | DESIGN REPORT INFORMATION | [5 empty] | DOT should provide a sample Design Report so everyone has the same expectation
PHDR - | 4.1 | Narrative | [5 empty] | Include project description, existing deficiencies, design solutions, typical section used, any design assumptions, maintenance/operations issues, etc.
PHDR - | 4.2 | Updated Design Criteria Form
PHDR - | 4.3 | Preliminary Traffic Analysis | [5 empty] | Signal warrants
Left and Right Turn Lane Warrants
LOS Calculations
Queue Length Calculations
Turning Lane Storage / Length Calculations
Segment Capacity
Signal Coordination Analysis
PHDR - | 4.4 | Pedestrian & Bicycle Accommodations
PHDR - | 4.5 | Superelevation Calculations | [5 empty] | This can be openroads generated reports showing the emax and superelevation transitions. Detailed superelevation transition calculations will be finalized at the Line and Grade submission.
PHDR - | 4.6 | Traffic Control Narrative | [5 empty] | Include discussion on temporary bicycle & pedestrian accommodations
PHDR - | 4.7 | Construction Schedule | [5 empty] | High level to determine project duration.
PHDR - | 4.8 | Geotechnical Issues
PHDR - | 4.9 | Engineering Report
PHDR - | 4.1 | Environmental | [5 empty] | Generate a list of environmental commitments with updates in matrix form. This will be a living document through the design phase.
List Purpose & Need statement for project
Figures showing existing and proposed watersheds for each outlet location
Potential outlets described with pre-development vs. post-development flow rates
MS4 and AoT treatment requirements identified
BMP locations and types identified
PHDR - | 4.11 | Preliminary Drainage | [5 empty] | Erosion and outlet protection identified
PHDR - | 4.12 | Utility Issues/Concerns | [5 empty] | Generally describe which utilities are impacted with locations and why impacts couldn't be avoided.
PHDR - | 4.13 | Study estimate | [5 empty] | Should be an updated version of the Pre-Hearing estimate, check high cost items and various percentages for appropriate values.
PHDR - | 4.14 | Utility Pole Relocation Sheet (Existing Poles Only)
PHDR - | 4.15 | List of Potential Utility Conflicts (Listed by Utility)
PHDR - | 4.16 | Any Pending/Outstanding Issues | [5 empty] | Has any issues that has not been addressed, need DOT input, or additional information been identified by the Consultant. Anything that could cause future delays.

## Slope & Drain (60%)
SLOPE & DRAIN SUBMISSION CHECKLIST
NOTE: THIS CHECKLIST IS EXPECTED TO BE MODIFIED AS THE STANDARDS FOR THE USE OF OPENROADS DESIGNER ARE DEVELOPED. USERS ARE ENCOURAGED TO CHECK THE NHDOT WEBSITE FOR AN UPDATED VERSION PRIOR TO USE.
[6 empty] | Version Date: | 2024-01-15 |  | Initials should be person who did the check.
PROJECT: | [8 empty] | The checker should be experienced.
ID |  | ITEM | DONE | DATE | CHECKED | DATE | REMARKS
|  |  | BY |  | BY
SDSC | 1 | REQUIRED SUBMISSION ITEMS
SDSC | 1.1 | Plans
SDSC | 1.2 | Design Report
SDSC | 1.3 | Drainage Report
SDSC | 1.4 | Quantity Calculations
SDSC | 1.5 | Utility Pole Relocation Sheet (Existing Poles Only)
SDSC | 1.6 | List of Utility Conflicts (Listed by Utility)
SDSC | 2 | REQUIRED DESIGN CHECKS
SDSC | 2.1 | Verify all comments from Line and Grade Plan Submission have been addressed.
SDSC | 2.2 | Vertical Curve vs. horizontal curve placement
SDSC | 2.3 | K values vs. Green Book standards
SDSC | 2.4 | Minimum/maximum grades vs. Green Book standards
SDSC | 2.5 | Turning lanes and intersections designs per Design Manual sample layouts
SDSC | 2.6 | Turn lanes, ramp lengths, etc. match traffic analysis
SDSC | 2.7 | Turning movements at all side roads and commercial driveways
SDSC | 2.8 | Intersection, passing, and stopping sight distances
SDSC | 2.9 | Verify project begins and ends in a convenient and logical location
SDSC | 2.1 | Verify property impacts are withing ROW or easements
SDSC | 2.11 | Intersection and ramp nose grading (show contours developed by model)
SDSC | 2.12 | Headlight Glare Screens
SDSC | 2.13 | Edge line profiles in superelevation transitions (show contours developed by model)
SDSC | 3 | PREVIOUS CHECKLISTS REVIEWED
SDSC | 4 | PLANS (ADDED INFORMATION FROM PREVIOUS SUBMISSION)
SDSC | 4.1 | TYPICAL SECTIONS
SDSC | 4.1.1 | Appropriate item numbers and nomenclature
SDSC | 4.1.2 | Aggregate base course material (Subgrade constants only for normal crown)
SDSC | 4.1.3 | Underdrain
SDSC | 4.1.4 | Special case typicals, i.e. side roads, curb details, etc.
SDSC | 4.1.5 | Pavement types and depths, pavement joint treatment (if required), pavement unit/mass
SDSC | 4.1.6 | Rock cuts consistent with Geotechnical Report
SDSC | 4.1.7 | Slope roundings (Only shown on the typicals not on each cross section)
SDSC | 4.1.8 | Superelevation treatment for shoulders (curbing treatment, if applicable)
SDSC | 4.1.9 | Curb, guardrail offset, median condition
SDSC | 4.1.10 | Maximum superelevation (E max)
SDSC | 4.1.11 | General notes specific to the project
SDSC | 4.1.12 | Drawn to scale (Note scale below each typical section)
SDSC | 4.2 | MISCELLANEOUS DETAIL SHEETS
SDSC | 4.2.1 | Include details as needed (examples follow)
SDSC | 4.2.2 | Sidewalk ramps |  |  |  |  | Available at Department website
SDSC | 4.2.3 | Driveway details |  |  |  |  | Available at Department website
SDSC | 4.2.4 | Curved guardrail with CRT Posts |  |  |  |  | Available at Department website
SDSC | 4.2.5 | Terminal Unit Delineation |  |  |  |  | Available at Department website
SDSC | 4.2.6 | EAGRT Platforms |  |  |  |  | Available at Department website
SDSC | 4.2.7 | Mid-Splice W-Beam guardrail stiffening |  |  |  |  | Available at Department website
SDSC | 4.2.8 | Pavement match detail
SDSC | 4.2.9 | Special drainage ditch details
SDSC | 4.2.10 | Stormwater BMPs
SDSC | 4.2.11 | Slope protection
SDSC | 4.2.12 | Retaining walls
SDSC | 4.2.13 | Special catch basins
SDSC | 4.2.14 | Permanent erosion control
SDSC | 4.2.15 | Concrete islands
SDSC | 4.3 | PLAN CUT SHEETS (add link to Sample Plans once created)
SDSC | 4.3.1 | Detail listed below is a baseline for General Plans. Additional detail (indicated in the respective sections below) to consolidate plan sets may be shown as room allows. All detail shown to 0.1 accuracy unless otherwise noted.
SDSC | 4.3.2 | Use engineering judgment if the precision is to be greater than noted.
SDSC | 4.4 | GENERAL
SDSC | 4.4.1 | North arrow (grid)
SDSC | 4.4.2 | Existing detail (exclude miscellaneous text such as curb, sidewalk, and woods type, etc.)
SDSC | 4.4.3 | Existing utilities
SDSC | 4.4.4 | Use correct symbols for detail
SDSC | 4.4.5 | Lettering must be legible when photographically reduced to 1/2 scale
SDSC | 4.4.6 | Match lines to abutting sheets
SDSC | 4.4.7 | Bench marks shown and described, if applicable
SDSC | 4.4.8 | CAROW Access points addressed
SDSC | 4.4.9 | Construction and Diversion Base line(s) labeled.
SDSC | 4.4.10 | PC, PT shown, (curve data or PI’s not required)
SDSC | 4.4.11 | Tree or bush annotations excluded
SDSC | 4.4.12 | Extend existing detail and alignment beyond project limits
SDSC | 4.4.13 | 250 ft ± beyond project limits on 1:50 plans
SDSC | 4.4.14 | 150 ft ± beyond project limits for 1:20 plans
SDSC | 4.4.15 | EP’s, TW’s, retaining walls, sidewalk
SDSC | 4.4.16 | Wetlands delineated and identified by number through the Bureau of Environment
SDSC | 4.4.17 | Invasive species areas delineated and identified by type through the Bureau of Environment
SDSC | 4.4.18 | Monitoring well locations
SDSC | 4.4.19 | Cross-hatch pavement removal outside slope lines
SDSC | 4.4.20 | Cross-hatch structure removal with bold line style
SDSC | 4.4.21 | Cross-hatch discontinued driveways outside of slope lines
SDSC | 4.5 | PROPOSED PERMANENT LAYOUT AND DETAIL
SDSC | 4.5.1 | Proposed work noted in upper case lettering
SDSC | 4.5.2 | EP’s, TW’s, retaining walls, sidewalk
SDSC | 4.5.3 | Curb without mark numbers
SDSC | 4.5.4 | Guardrail and terminal units. (Guardrail notes are not required)
SDSC | 4.5.5 | Slope lines and clearing lines
SDSC | 4.5.6 | Clearing and grubbing areas shown and labeled.
SDSC | 4.5.7 | Fences, pedestrian rail, and bike rail labeled
SDSC | 4.5.8 | Signal mast arms (signal heads, pullboxes etc. not required)
SDSC | 4.5.9 | Drainage (See Drainage Guidelines for more information)
SDSC | 4.5.10 | Closed drainage system and culverts with flow arrows and drainage note callouts
SDSC | 4.5.11 | Drive pipes shown
SDSC | 4.5.12 | Stone protection
SDSC | 4.5.13 | Erosion control treatment and/or water quality treatment shown and labeled, if appropriate
SDSC | 4.5.14 | Proposed utilities (If known)
SDSC | 4.5.15 | Overhead Sign Structures (sign text not required)
SDSC | 4.6 | ROW
SDSC | 4.6.1 | Parcel numbers and owner names as shown on abstracting plan
SDSC | 4.6.2 | ROW type labeled similar to ROW Plans
SDSC | 4.6.3 | Right-of-Way bounds shown
SDSC | 4.6.4 | Fence LAROW with chain link or woven wire, as appropriate
SDSC | 4.6.5 | All easements shown, including maintenance of detention basins, ditches, etc..
SDSC | 4.6.6 | Easements labeled (do not shade or hatch)
SDSC | 4.7 | NOTES
SDSC | 4.7.1 | Road names (on each cut sheet)
SDSC | 4.7.2 | No ROW notes (alignment radius, flagging etc.)
SDSC | 4.7.3 | Limits of work and approach notes
SDSC | 4.7.4 | Begin and End Project notes
SDSC | 4.7.5 | Notes to “SAVE” or “SAVE IF POSSIBLE” or “Remove” trees, shrubs, etc.
SDSC | 4.7.6 | At or near slope lines, if questionable or resulting from Right-of-Way commitments.
SDSC | 4.7.7 | Special construction notes (i.e. “REMOVE EXISTING PAVEMENT, PLACE HUMUS & SLOPE SEED”.)
SDSC | 4.7.8 | Buildings to be demolished. If subject to prior removal, show date and cross hatch per ROW checklist
SDSC | 4.7.9 | Projects with CAROW, note under the property owner’s name the number of access points granted.
SDSC | 4.7.10 | Even if it is zero. If the driveway will be constructed in the future, note the future location.
SDSC | 4.7.11 | Drainage notes |  |  |  |  | Provide on separate sheet if needed
SDSC | 4.7.12 | Quantity match lines (QML)
SDSC | 4.7.13 | Graphic scale
SDSC | 4.8 | PROFILES
SDSC | 4.8.1 | Station and scale construction Base Line (same as on plan sheets)
SDSC | 4.8.2 | Finish grade (bold line)
SDSC | 4.8.3 | Original ground to nearest 0.1 foot and finish grade 0.01 foot
SDSC | 4.8.4 | Rock line plotted
SDSC | 4.8.5 | Normal high water labeled
SDSC | 4.8.6 | Vertical curve data (including low points and high points)
SDSC | 4.8.7 | Vertical curve information - VPI’s PVC’s, PVT’s, Curve Length, K Value
SDSC | 4.8.8 | Grades, equations, bridges, rivers, and streams labeled
SDSC | 4.8.9 | Profile datum
SDSC | 4.8.10 | Show superelevation rates and transitions
SDSC | 4.8.11 | Show proposed subgrade treatments including areas of extra sand
SDSC | 4.8.12 | Begin and end of project notes
SDSC | 4.8.13 | Limit of work and approach notes
SDSC | 4.8.14 | Check profile elevations vs. cross-sections
SDSC | 4.8.15 | Graphic scale
SDSC | 4.9 | DRAINAGE AND UTILITY PLANS
SDSC | 4.9.1 | North arrow (grid)
SDSC | 4.9.2 | Include drainage notes on Drainage and Utility Plans, if space allows. The guidelines for writing drainage notes, see Appendix 13-10 Drainage Note Format. If these plans are too crowded, include the notes on a separate sheet placed prior to the first Drainage and Utility plan sheet.
SDSC | 4.9.3 | Write drainage notes per the standard guidelines
SDSC | 4.9.4 | Existing ROW, (proposed) ROW, easements and property owners as noted on General Plans
SDSC | 4.9.5 | Slope lines labeled
SDSC | 4.9.6 | Construction Base Line(s) labeled (Diversion Base Line not required)
SDSC | 4.9.7 | PC's and PT's shown but no curve data or PI's
SDSC | 4.9.8 | Proposed TW’s, EP’s, drives curbing, retaining walls, sidewalk and guardrail (include existing guardrail, if it’s to remain in place). (Turning lane lines, stop bars, arrows etc. are not required.)
SDSC | 4.9.9 | All drainage with flow arrows
SDSC | 4.9.10 | Existing Drainage labeled
SDSC | 4.9.11 | Wetlands delineated and identified by number
SDSC | 4.9.12 | Streams, brooks, rivers, etc.
SDSC | 4.9.13 | Stone inlet and outlet protection
SDSC | 4.9.14 | Permanent erosion control shown and labeled
SDSC | 4.9.15 | Existing Utilities (underground and aerial) with annotation
SDSC | 4.9.16 | Existing utility poles flagged and labeled "R" (remove) only
SDSC | 4.9.17 | Existing underground utilities shown and labeled (i.e., "to be abandoned in place", "to be removed", etc.) (If Known)
SDSC | 4.9.18 | Proposed utility poles flagged (per symbol sheet)
SDSC | 4.9.19 | Existing and proposed drainage and utilities
SDSC | 4.9.20 | Pertinent existing detail
SDSC | 4.9.21 | Beginning and end project notes, limit of work or ex. TW’s, EP’s, drives, sidewalks, etc. are not required
SDSC | 4.9.22 | Existing and proposed signal mast arms or pedestals and lighting
SDSC | 4.9.23 | (NOTE: Existing and proposed pullboxes, conduit, and control cabinets are not required but are always checked for conflicts)
SDSC | 4.9.24 | Proposed overhead sign structures (sign text not required)
SDSC | 4.9.25 | Road Names
SDSC | 4.9.26 | Monitoring Wells
SDSC | 4.9.27 | Graphic Scale
SDSC | 4.1 | ALIGNMENT, CURBING, AND PAVEMENT LAYOUT PLANS
SDSC | 4.10.1 | North arrow (grid)
SDSC | 4.10.2 | Construction Base Line(s) labeled (Diversion Base Line not required)
SDSC | 4.10.3 | Construction Base Line with equations (to 0.01 accuracy)
SDSC | 4.10.4 | Bearings, curve data -- PC’s PT’s and PI’s (include PI coordinates) (to 0.01 accuracy)
SDSC | 4.10.5 | Survey SDR traverse points with elevations (to 0.01 accuracy)
SDSC | 4.10.6 | Begin and end taper notes (station, offset, and rate)
SDSC | 4.10.7 | Roadway dimensions and drive widths
SDSC | 4.10.8 | Drive radii shown and tangent point offsets at the roadway match labeled (to 0.01 accuracy)
SDSC | 4.10.9 | All roadway intersection radius and tangential point offsets labeled
SDSC | 4.10.10 | Proposed curb shown as heavy linestyle
SDSC | 4.10.11 | Proposed EP’s, TW’s, lane lines, edge of sidewalk, and guardrail
SDSC | 4.10.12 | Driveway notes
SDSC | 4.10.13 | Curbing general notes, (required only on the first sheet of this series)
SDSC | 4.10.14 | Existing TW’s, EP’s and driveways are not required
SDSC | 4.10.15 | Road names
SDSC | 4.10.16 | Match lines to abutting sheets
SDSC | 4.10.17 | Graphic scale
SDSC | 4.11 | PAVEMENT MARKING PLANS
SDSC | 4.11.1 | North arrow (grid)
SDSC | 4.11.2 | Construction Base Line(s) labeled (Diversion Base Line not required)
SDSC | 4.11.3 | Construction Base Line with equations.
SDSC | 4.11.4 | Begin and end taper notes (station, offset, and rate)
SDSC | 4.11.5 | Proposed curb shown as heavy linestyle
SDSC | 4.11.6 | Proposed EP’s, TW’s, lane lines, and edge of sidewalk
SDSC | 4.11.7 | Lane usage, i.e., arrows, words
SDSC | 4.11.8 | Crosswalk and stop bars
SDSC | 4.11.9 | Pavement marking general notes, (required only on the first sheet of this series)
SDSC | 4.11.10 | Existing TW’s, EP’s and driveways are not required
SDSC | 4.11.11 | Road names
SDSC | 4.11.12 | Match lines to abutting sheets
SDSC | 4.11.13 | Graphic scale
SDSC | 4.12 | SIGNAL PLANS
SDSC | 4.12.1 | North arrow (grid)
SDSC | 4.12.2 | Appropriate scale 1:20
SDSC | 4.12.3 | Construction Base Line(s) labeled
SDSC | 4.12.4 | Existing conduit, pullboxes, mast arms, controller cabinets, meter pedestals
SDSC | 4.12.5 | Right-of-Way lines (as noted on the General Plans)
SDSC | 4.12.6 | Proposed EP’s, TW’s, curbing, pavement markings, (arrows, crosswalks, stop bars, etc.)
SDSC | 4.12.7 | Specific line description, i. e., 4-inch SSL (w) not required
SDSC | 4.12.8 | Underground utilities, and existing and proposed drainage
SDSC | 4.12.9 | “Soil Borings” summary box and boring location with appropriate symbol
SDSC | 4.12.10 | Proposed meter pedestal, controller cabinet, conduit and pull boxes for signals and lighting,
SDSC | 4.12.11 | Proposed power source shown
SDSC | 4.12.12 | Proposed mast arm lengths shown
SDSC | 4.12.13 | Proposed vehicle detection shown (cameras, loops, detection zones, etc.)
SDSC | 4.12.14 | Signal timing plan
SDSC | 4.12.15 | Phasing diagram
SDSC | 4.12.16 | Signal head diagrams
SDSC | 4.12.17 | Traffic flow diagram with am/pm peak hours
SDSC | 4.12.18 | Fire pre-emption system (if requested by the Town/City)
SDSC | 4.12.19 | General notes
SDSC | 4.12.20 | Road names
SDSC | 4.12.21 | Graphic scale
SDSC | 4.13 | TRAFFIC CONTROL PLANS
SDSC | 4.13.1 | Narrative explaining TCP details should be included (this is typically shown on the first TCP sheet)
SDSC | 4.13.2 | Existing detail (as noted on the general plans)
SDSC | 4.13.3 | Proposed EP’s, TW’s, and drives as necessary
SDSC | 4.13.4 | Temporary widenings, EP’s and/or TW’s
SDSC | 4.13.5 | Existing and proposed drainage, including temporary drainage
SDSC | 4.13.6 | Check constructability of drainage (i.e. 12 feet deep but 1 foot off TW).
SDSC | 4.13.7 | Show proposed drainage constructed in previous phases
SDSC | 4.13.8 | Check impacts that will occur when excavating to remove existing, or place new, drainage systems.
SDSC | 4.13.9 | Concrete barrier, temporary guardrail, impact attenuators
SDSC | 4.13.10 | Temporary widening shaded to differentiate from proposed work
SDSC | 4.13.11 | Slope lines (temporary and proposed), label if unclear
SDSC | 4.13.12 | Legend box , if necessary, with different shading to denote phased construction
SDSC | 4.13.13 | Utilities (existing and proposed), as necessary
SDSC | 4.13.14 | Delineated wetlands
SDSC | 4.13.15 | Easements
SDSC | 4.13.16 | Pavement markings with line descriptions (i. e., 4-inch SSL (w))
SDSC | 4.13.17 | Temporary lighting with notes
SDSC | 4.13.18 | Property owners names and parcel numbers
SDSC | 4.13.19 | North arrow (grid)
SDSC | 4.13.20 | Graphic scale
SDSC | 4.14 | DIVERSION PLANS
SDSC | 4.14.1 | Existing detail (as noted on the general plans)
SDSC | 4.14.2 | Diversion and Construction Base line(s) labeled
SDSC | 4.14.3 | Diversion Base Line with equations
SDSC | 4.14.4 | Diversion bearings, curve data -- PC’s PT’s and PI’s (including PI coordinates)
SDSC | 4.14.5 | Diversion EP’s and TW’s
SDSC | 4.14.6 | Slope lines and clearing lines
SDSC | 4.14.7 | Taper notes and offsets
SDSC | 4.14.8 | Temporary signals (approximate locations)
SDSC | 4.14.9 | Existing and proposed drainage, including temporary drainage
SDSC | 4.14.10 | Show proposed drainage constructed in previous phases
SDSC | 4.14.11 | Utilities (existing and proposed), as necessary
SDSC | 4.14.12 | ROW and property lines (as noted on General plans)
SDSC | 4.14.13 | Easements labeled (do not shade or hatch)
SDSC | 4.14.14 | Parcel numbers and owner names (as noted on General Plans)
SDSC | 4.14.15 | Drive notes
SDSC | 4.14.16 | Match lines to abutting sheets
SDSC | 4.14.17 | Radii labeled and offsets shown
SDSC | 4.14.18 | Roadway dimensions
SDSC | 4.14.19 | Concrete barrier, temporary guardrail, impact attenuators
SDSC | 4.14.20 | Delineated Wetlands
SDSC | 4.14.21 | North arrow (grid)
SDSC | 4.14.22 | Graphic scale
SDSC | 4.15 | CROSS SECTIONS
SDSC | 4.15.1 | EXISTING DETAIL
SDSC | 4.15.1.1 | Existing ground shown
SDSC | 4.15.1.2 | TW’s, EP’s, curb, woods, center of road, guardrail, retaining wall, edge of river,
SDSC | 4.15.1.3 | Stone walls, fences, and delineated wetland(s) labeled
SDSC | 4.15.1.4 | Trees and poles with annotation and station (include lights on poles). | [5 empty] | *ORD
SDSC | 4.15.1.5 | Typically, only plot small and large trees per Spec. Book | [5 empty] | *ORD
SDSC | 4.15.1.6 | Label bushes (ornamental or special landscaping etc.) if at or near the slope lines and is to be saved. | [5 empty] | *ORD
SDSC | 4.15.1.7 | CB’s, DI’s, manholes, etc. with station | [5 empty] | *ORD
SDSC | 4.15.1.8 | Drainage pipes with size and flow arrow | [5 empty] | *ORD
SDSC | 4.15.1.9 | Underground utilities shown on all sections. Describe the utility on the first section of the cut sheet
SDSC | 4.15.1.10 | Houses and building sills with elevations | [5 empty] | *ORD
SDSC | 4.15.1.11 | Signal, light pole, and sign foundations | [5 empty] | *ORD
SDSC | 4.15.2 | MISCELLANEOUS LABELING
SDSC | 4.15.2.1 | Pavement slopes 2%, 8%, of each lane and shoulder (including sidewalk) | [5 empty] | *ORD
SDSC | 4.15.2.2 | Side Slopes 6:1, 4:1, varies etc.
SDSC | 4.15.2.3 | Existing utility poles flagged and labeled "R" (remove) only | [5 empty] | *ORD
SDSC | 4.15.2.4 | Existing underground utilities shown and labeled (i.e., "to be abandoned in place", "to be removed", etc.) (If Known) | [5 empty] | *ORD
SDSC | 4.15.2.5 | Lane and shoulder widths (May only label the first section on the cut sheet, unless in a taper) | [5 empty] | *ORD
SDSC | 4.15.2.6 | Dimension grass panels, ditch offsets, etc. if not per typical
SDSC | 4.15.2.7 | Drive dimensions at each break in slope along the drive and label the slope (%)
SDSC | 4.15.2.8 | Existing drainage to be removed (label “REMOVE”) | [5 empty] | *ORD
SDSC | 4.15.2.9 | Quantity match lines (QML)
SDSC | 4.15.2.10 | Label offset from Construction Base Line to Diversion Base Line
SDSC | 4.15.2.11 | Only needed if separate Diversion cross sections are not included
SDSC | 4.15.2.12 | Note trees that require specific treatment, i.e., “SAVE, REMOVE, or SAVE, IF POSSIBLE”. | [5 empty] | *ORD
SDSC | 4.15.3 | GENERAL
SDSC | 4.15.3.1 | Plot rock and muck lines
SDSC | 4.15.3.2 | Diversion “top line template” and bottom of aggregate base shown by dashed line.
SDSC | 4.15.3.3 | Slope line “tick marks” reflect appropriate slope rounding
SDSC | 4.15.3.4 | Transition embankment slopes correctly
SDSC | 4.15.3.5 | Develop sections in rock areas @ +25 stationing
SDSC | 4.15.3.6 | Existing ground elevations (tenth) and finish grade elevations (hundredth).
SDSC | 4.15.3.7 | Roadway names and State project number
SDSC | 4.15.3.8 | Guardrail areas, (include extended shoulder break and guardrail platforms)
SDSC | 4.15.3.9 | Show stabilization of steep slopes (cut or fill) (stone slope protection or terracing)
SDSC | 4.15.3.10 | Notes for “Begin and End Construction”, and “Limit of Work”
SDSC | 4.15.3.11 | Proposed granite curb
SDSC | 4.15.3.12 | Drives designed per Driveway Manual and detail sheet
SDSC | 4.15.4 | DRAINAGE, UTILITIES, SIGN STRUCTURES, AND SIGNALS
SDSC | 4.15.4.1 | Ditch elevations and flow arrows
SDSC | 4.15.4.2 | Proposed drainage shown per symbol legend, drawn to correct offset and size | [5 empty] | *ORD
SDSC | 4.15.4.3 | Labeled and referenced by flagging the note number at the CB or pipe | [5 empty] | *ORD
SDSC | 4.15.4.4 | Outlet stone protection shown | [5 empty] | *ORD
SDSC | 4.15.4.5 | Correct structure top shown (slab top or cone) | [5 empty] | *ORD
SDSC | 4.15.4.6 | Granular backfill “box” for underdrain | [5 empty] | *ORD
SDSC | 4.15.4.7 | Cross-pipe flow arrows | [5 empty] | *ORD
SDSC | 4.15.5 | DESIGN CHECKS
SDSC | 4.15.5.1 | Cross section template matches the typical sections
SDSC | 4.15.5.2 | Slope line “tick marks” match plan sheet slope lines
SDSC | 4.15.5.3 | Verify Existing ground elevations and finish grade elevations match profile
SDSC | 4.15.5.4 | Can slopes be steepened to minimize the wetland impacts?
SDSC | 4.15.5.5 | Can slopes be flattened to eliminate/minimize the need for guardrail?
SDSC | 4.15.5.6 | Will guardrail effect sight distance along road, at drives or side streets, or at bridges?
SDSC | 4.15.5.7 | Will retaining walls be needed to minimize slope impacts to private property?
SDSC | 4.15.5.8 | Have required Geotechnical recommendations been shown
SDSC | 4.15.6 | DETOUR SECTIONS
SDSC | 4.15.6.1 | Provide same information as regular cross section
SDSC | 4.15.6.2 | Temporary drainage (labeled similar to proposed)
SDSC | 4.15.6.3 | Special notes
SDSC | 5 | DRAINAGE DESIGN GUIDELINES
SDSC | 5.0.1 | Look at the “Big Picture”. Will it work?
SDSC | 5.0.2 | Does the design take into account phased construction and multi-project involvement?
SDSC | 5.0.3 | Are the outlets in an appropriate location?
SDSC | 5.0.4 | Permanent erosions control measures are designed for Q2 but need to handle Q10.
SDSC | 5.0.5 | Check to ensure drainage design doesn’t drain a wetland.
SDSC | 5.0.6 | For pipe jacking locations, need additional soils information.
SDSC
SDSC | 5.1 | Drainage Review Field Trip
SDSC | 5.1.1 | Check designated watershed areas.
SDSC | 5.1.2 | Review existing drainage flow patterns.
SDSC | 5.1.3 | Check sizes of existing pipes upstream and downstream of the proposed installation. Also the type of pipe (metal, concrete, etc.)
SDSC | 5.1.4 | Check existing pipes and CBs for condition and size. Check water level marks in pipes.
SDSC | 5.1.5 | Talk to District for any problems.
SDSC | 5.1.6 | Take picture of concerns, especially outlet areas.
SDSC | 5.1.7 | Review proposed outlet areas, especially for permanent erosion control consideration.
SDSC | 5.2 | Closed Drainage Systems
SDSC | 5.2.1 | If possible, use existing CBs and pipes if they are in good condition.
SDSC | 5.2.2 | Closed system requires CBs every 300 ft. minimum.
SDSC | 5.2.3 | CBs and flankers in sags and low points. Also on steep grades.
SDSC | 5.2.4 | Have CBs been placed at super transitions (rollover point).
SDSC | 5.2.5 | Have CBs been placed in “snow curb” areas.
SDSC | 5.2.6 | Have CBs been placed at the downstream end of curbing
SDSC | 5.2.7 | Verify the correct type of grate is being used. (C grates can be used in areas where traffic could never hit it)
SDSC | 5.2.8 | Check grate capacity
SDSC | 5.2.9 | Check spread width along gutter
SDSC | 5.2.10 | Verify CB spacing prevents spread of water to exceed design standard
SDSC | 5.2.11 | Check rim elevation calculations (1.5" below wearing course elevation)
SDSC | 5.2.12 | Check minimum pipe size requirements. (under pavement (15”), parallel to road and for slope drains (12”))
SDSC | 5.2.13 | Check minimum pipe cover requirements. (under pavement (4ft.), other (2ft.))
SDSC | 5.2.14 | Verify use of 3-inch drops from inlet to outlet in CBs.
SDSC | 5.2.15 | Crowns of pipes at same elevation when upsizing pipes in CBs.
SDSC | 5.2.16 | Are minimum pipe slopes being met? (0.4% or able to maintain 2 fps while flowing one-third full)
SDSC | 5.2.17 | Check CB sizes, are larger basins required due to number and size of pipes entering CB
SDSC | 5.2.18 | Are slab tops noted when cover over pipe is reduced
SDSC | 5.2.19 | Eccentric cones used to provide horizontal offset.
SDSC | 5.2.20 | Use separate systems for underdrain and carrying pipes.
SDSC | 5.2.21 | Avoid using deep structures, use drop manholes to go down steep slopes.
SDSC | 5.2.22 | Can structures and pipes be kept within the 9 ft. subsidiary excavation limits?
SDSC | 5.2.23 | Check velocity in pipes, use CMP to slow velocity down. (15 fps or less, 10 fps ideal)
SDSC | 5.2.24 | Are energy dissipaters required to slow velocities?
SDSC | 5.2.25 | Can drainage system be moved away from rock cut areas?
SDSC | 5.2.26 | Are CBs placed upgrade prior to bridges?
SDSC | 5.2.27 | Can underdrains outlet? Have flushing basins been added in runs over 600 ft.
SDSC | 5.2.28 | Minimize the number of pipe crossings on high volume roads
SDSC | 5.2.29 | Has appropriate outlet protection been used?
SDSC | 5.2.30 | Can drainage be moved to avoid utility conflicts?
SDSC | 5.2.31 | Is bit curb required under guardrail, has drainage been included?
SDSC | 5.2.32 | Does drainage conflict with guardrail posts
SDSC
SDSC | 5.3 | Culvert Design
SDSC | 5.3.1 | Verify correct design storm has been used
SDSC | 5.3.2 | Check minimum culvert size requirements have been met
SDSC | 5.3.3 | Culverts with spans greater than 10 ft. are considered bridges
SDSC | 5.3.4 | Check minimum grade requirements have been met (greater than 0.4% or maintain 2 fps while flowing one-third full)
SDSC | 5.3.5 | Align culvert with natural inlet and outlet channels if possible
SDSC | 5.3.6 | Anti-Seep collars on culverts steeper than 20%
SDSC | 5.3.7 | Has appropriate outlet protection been used?
SDSC | 5.3.8 | Check maximum headwater depth for property impacts, damage to roadway, encroachment in structural section, and traffic interruption, hazardous condition, etc.
SDSC | 5.3.9 | Check headwater to diameter ratio
SDSC | 5.3.10 | Check minimum cover depths under pavement (4 ft.), under drives (1 ft.) and under grassed areas (2 ft.).
SDSC | 5.3.11 | Headers not required on culverts up to 18” unless at an active stream
SDSC | 5.3.12 | End sections should be used instead of headers for culverts less than 48” where field conditions permit. End Sections should not be used in a headwater condition
SDSC | 5.3.13 | Follow NHDES stream crossing guidelines
SDSC | 5.3.14 | How will existing drainage flow be maintained during construction of new culvert
SDSC
SDSC | 5.4 | Ditchline Drainage Design
SDSC | 5.4.1 | Maximum length of 400 ft. for ditches between CBs.
SDSC | 5.4.2 | Minimum ditch grade of 0.5% when possible.
SDSC | 5.4.3 | Review ditch flow calculations for potential erosion problems. Stone line ditch if necessary.
SDSC | 5.4.4 | Review ditch line flows at cut to fill slope interface to ensure no erosion.
SDSC | 5.4.5 | Ditches along aquifers and water supplies shall be lined in accordance with governing environmental agencies.
SDSC | 5.4.6 | Typical Manning’s number for ditches and channels is n=0.03 to 0.10
SDSC | 5.4.7 | Check ditch size to ensure ditch will handle the runoff flows.
| *ORD | Typically, information shown back and ahead of stations is not required using OpenRoads, new standards are under development, coordinate with NHDOT PM on approach.

## Utility Plans (75%)
UTILITY PLANS SUBMISSIOM CHECKLIST
This submission is intended to provide the utility companies with plans that reflect complete alignments, near complete drainage systems, edge of pavements, guardrail, right of way information and the like. The submission shall include one (1) pdf electronic file of following plans and documents noted below. Coordinate with the Utility Coordinator for the need of and number of hardcopies of this submission.
[6 empty] | Version Date: | 2024-10-08 | Initials should be person who did the check.
PROJECT: | [7 empty] | The checker should be experienced.
ID |  | ITEM | DONE | DATE | CHECKED | DATE | REMARKS
|  |  | BY |  | BY
UPSC | 1 | REQUIRED SUBMISSION ITEMS
UPSC | 1.1 | UTILITY POLE RELOCATION SHEET
UPSC | 1.1.1 | Indicate utility pole and aerial conflicts
UPSC | 1.2 | UTILITY CONFLICT LISTS (Separate by Utility)
UPSC | 1.2.1 | Indicate proposed construction conflict
UPSC | 1.2.2 | Indicate construction activities conflict
UPSC | 1.2.3 | Indicate surface conflicts
UPSC | 2 | PLANS (Added information from previous submission)
UPSC | 2.1 | Include sheet numbers on all sheets (manually, if necessary).
UPSC | 2.1.1 | FRONT SHEET
UPSC | 2.1.1.1 | Latest revision date verified
UPSC | 2.2.1 | INDEX OF SHEETS AND GENERAL NOTES
UPSC | 2.2.1.1 | Latest revision date verified
UPSC | 2.3.1 | STANDARD SYMBOLS
UPSC | 2.3.1.1 | Latest revision date verified
UPSC | 2.4.1 | TYPICAL SECTIONS
UPSC | 2.4.1.1 | Incorporate utility related Slope and Drain comments
UPSC | 2.5.1 | BRIDGE PLANS
UPSC | 2.5.1.1 | GENERAL PLAN AND ELEVATION
UPSC | 2.5.1.1.1 | Existing Utilities shown
UPSC | 2.5.1.2 | SITE PLAN AND PROFILE
UPSC | 2.5.1.2.1 | Existing Utilities shown
UPSC | 2.5.1.2.2 | Aerial lines between poles and structures shown
UPSC | 2.5.1.3 | ABUTMENT MASONRY PLANS AND ELEVATIONS
UPSC | 2.5.1.3.1 | Existing Utilities shown if rehabilitation
UPSC | 2.5.1.4 | TYPICAL BRIDGE SECTION AND DETAILS
UPSC | 2.5.1.4.1 | Existing Utilities shown
UPSC | 2.6.1 | GENERAL PLANS
UPSC | 2.6.1.1 | GENERAL
UPSC | 2.6.1.1.1 | Incorporate utility related Slope and Drain comments
UPSC | 2.6.1.1.2 | Near-Final drainage design complete
UPSC | 2.6.1.1.3 | Right of Way lines (existing, proposed, easements (temporary and permanent). This shall incorporate the Preliminary ROW plan comments.
UPSC | 2.6.1.1.4 | Erosion and Sediment control features included
UPSC | 2.6.1.1.5 | Tree or bush annotations excluded
UPSC | 2.6.1.1.6 | Drive locations
UPSC | 2.6.1.1.7 | Sidewalks
UPSC | 2.6.1.1.8 | Building Demolitions
UPSC | 2.6.1.1.9 | EPs, TWs, retaining walls, guardrail limits
UPSC | 2.6.1.1.10 | Existing Utilities
UPSC | 2.6.1.2 | PROPOSED PERMANENT LAYOUT AND DETAIL
UPSC | 2.6.1.2.1 | Curb without mark numbers
UPSC | 2.6.1.2.2 | Begin/End Construction notes and Limit of Work notes
UPSC | 2.6.1.2.3 | Guardrail and terminal units
UPSC | 2.6.1.2.4 | Slope lines and clearing lines
UPSC | 2.6.1.2.5 | Clearing and grubbing areas designated by letters (no shading required)
UPSC | 2.6.1.2.6 | (NOTE: If a tree (small or large) is near a clearing area, include it within the clearing and have the letter designation point to the tree)
UPSC | 2.6.1.2.7 | Fences, pedestrian rail, and bike rail labeled
UPSC | 2.6.1.2.8 | Signal mast arms and conduit locations
UPSC | 2.6.1.2.9 | Lighting and conduit locations
UPSC | 2.6.1.2.10 | Drainage
UPSC | 2.6.1.2.11 | Closed drainage system and culverts with flow arrows
UPSC | 2.6.1.2.12 | Stone protection
UPSC | 2.6.1.2.13 | Underdrain
UPSC | 2.6.1.2.14 | Erosion control treatment and/or water quality treatment shown and labeled, if appropriate
UPSC | 2.6.1.2.15 | Proposed Utilities (If Known)
UPSC | 2.6.1.2.16 | Overhead Sign Structures (sign text not required)
UPSC | 2.6.1.3 | DRAINAGE AND UTILITY PLANS
UPSC | 2.6.1.3.1 | Incorporate utility related Slope and Drain comments
UPSC | 2.6.1.3.2 | Existing utilities labeled (size,material, utility)
UPSC | 2.6.1.4 | DRAINAGE NOTES
UPSC | 2.6.1.4.1 | Complete - Incorporate utility related Slope and Drain comments
UPSC | 2.6.1.5 | PROFILES
UPSC | 2.6.1.5.1 | Complete - Incorporate utility related Slope and Drain comments
UPSC | 2.6.1.6 | TEMPORARY DIVERSION AND/OR DETOUR PLANS
UPSC | 2.6.1.6.1 | Incorporate utility related Slope and Drain comments
UPSC | 2.6.1.7 | TRAFFIC CONTROL PLANS
UPSC | 2.6.1.7.1 | Incorporate utility related Slope and Drain comments
UPSC | 2.6.1.7.2 | Include construction phasing narrative/sequencing
UPSC | 2.6.1.8 | CROSS SECTIONS
UPSC | 2.6.1.8.1 | Incorporate utility related Slope and Drain comments
UPSC | 2.6.1.8.2 | Finalized template plotted
UPSC | 2.6.1.8.3 | Existing utilities plotted and missing utilities noted
UPSC | 2.6.1.9 | DETOUR SECTIONS
UPSC | 2.6.1.9.1 | Incorporate utility related Slope and Drain comments

## Wetland Plans
WETLAND PLANS SUBMISSION CHECKLIST
NOTE: THIS CHECKLIST IS EXPECTED TO BE MODIFIED AS THE STANDARDS FOR THE USE OF OPENROADS DESIGNER ARE DEVELOPED. USERS ARE ENCOURAGED TO CHECK THE NHDOT WEBSITE FOR AN UPDATED VERSION PRIOR TO USE.
[5 empty] | Version Date: | 2024-10-08 | Initials should be person who did the check.
PROJECT: | [6 empty] | The checker should be experienced.
ID | ITEM | DONE | DATE | CHECKED | DATE | REMARKS
|  | BY |  | BY
PLANS (TO BE SUBMITTED WITH WETLAND PERMIT APPLICATION)
FRONT SHEET (add link to Sample Plans once created)
LOCATION MAP
Project location designated with a circle
State Project Number attached to circle
North arrow (State of NH)
Major roads labeled
Town, city, county & state names labeled and boundaries shown
Rivers, brooks, streams, lakes, etc. labeled
Railroads (RR) labeled
Graphic Scale
LAYOUT
Existing buildings (solid), roadway edge of pavement (E.P.), drive E.P.'s, curbing, bridges, railroads
Labels for roads, railroad crossings, town/city, and town/county/state boundaries
Existing rivers, streams, brooks and lakes
Labels for water bodies and waterways with flow arrows
"To (Town or City)" at all ends of the project with destination arrows
North arrow (grid)
Town/City of ( )
County of ( )
Numeric Scale
Begin and End Construction with Station
Limit of Work with Station
Construction Alignment with stationing labeled at interval appropriate for the scale
Delineated wetlands shown if visible with scale used
Designated wetland impact areas with dashed box and sheet number noted (see sample plan)
| This may only be necessary for corridor projects | -----------------------------------------------------------------------------------------------------------------
MISCELLANEOUS
Project name & (Federal and State) numbers
Road name in sheet title
"Drawn by" and "Checked by"
Sheet numbers and project numbers
Sheet titled "Wetland Plans"
Submission stamp
Index of Sheets
Wetlands delineated by certified wetland scientist note
Note "FOR CONSTRUCTION DETAILS - SEE CONSTRUCTION PLANS"
STANDARD SYMBOL SHEETS
| Latest revision date verified |  |  |  |  | Available at Department website
WETLAND PLAN CUT SHEETS (add link to Sample Plans once created)
WETLAND IMPACT SUMMARY (Plan Sheet)
Wetland classification code chart
Wetland impact summary table
| This sheet can be omitted if both exhibits can be reasonably fit on the first Plan sheet | -----------------------------------------------------------------------------------------------------------------
GENERAL
Wetland impact legend (include on every plan sheet)
Existing detail including delineated wetlands and 100-year floodplain
| Exclude miscellaneous text such as curb types, sidewalk types, tree and utility annotations, etc.) | -----------------------------------------------------------------------------------------------------------------
Wetland designation triangles and classification labels shown
TOB, OHW, TBZ and TOBOHW line designations shown
Road names
Alignment(s) labeled (construction and diversion)
| Omit curve data, PC's, PT's and PI's | -----------------------------------------------------------------------------------------------------------------
North arrow
Graphic Scale
Parcel number and owner's name
ROW lines and property lines
Proposed ROW: label ROW, LAROW or CAROW on all cut sheets
Existing ROW: label "Approximate Existing ROW" appropriately on all cut sheets
PROPOSED DETAIL
Begin/End Construction notes and Limit of Work notes
T.W.'s, E.P.'s, curbing, sidewalks, retaining walls and guardrail
Slope lines and clearing lines
Pertinent slope line and clearing notes (i.e. Clear to Slope Line Only)
Wetland impacts (shown with shading)
Wetland impact location letter(s) shown
Fence, pedestrian trail, bike trail
Easements shown and labeled (do not shade or hatch)
Drainage
Closed drainage system with flow arrows and outlet pipe sizes
Culverts, labeled with flow arrows and pipe sizes
Stone protection locations
EROSION CONTROL PLAN CUT SHEETS (add link to Sample Plans once created)
EROSION CONTROL STRATEGIES (Plan Sheet)
Check revision date to ensure the use of up-to-date materials
GENERAL
Erosion Control Plan Legend (include on every plan sheet)
Existing detail including delineated wetlands and 100-year floodplain
| Exclude miscellaneous text such as curb types, sidewalk types, tree and utility annotations, etc.) | -----------------------------------------------------------------------------------------------------------------
Road names
Alignment(s) labeled (construction and diversion)
| Omit curve data, PC's, PT's and PI's | -----------------------------------------------------------------------------------------------------------------
North arrow
Graphic Scale
Parcel number and owner's name
ROW lines and property lines
Proposed ROW: label ROW, LAROW or CAROW on all cut sheets
Existing ROW: label "Approximate Existing ROW" appropriately on all cut sheets
Existing Contours (2 foot interval)
PROPOSED DETAIL
Begin/End Construction notes and Limit of Work notes
T.W.'s, E.P.'s, curbing, sidewalks, retaining walls and guardrail
Slope lines and clearing lines
Wetland impacts
Proposed Contours (2 foot interval)
Fence, pedestrian trail, bike trail
Easements shown and labeled (do not shade or hatch)
Drainage
Closed drainage system with flow arrows and outlet pipe sizes
Culverts, labeled with flow arrows and pipe sizes
Stone protection locations
Erosion Control Strategy lines (indicating perimeter control, channel protection, etc.)
ADDITIONAL CONSIDERATIONS
| A construction narrative should be provided as part of the whole permit package | -----------------------------------------------------------------------------------------------------------------
| Plan sheets such as slope stabilization details or longitudinal channel/pipe profiles may be needed | -----------------------------------------------------------------------------------------------------------------
| Ultimately, work with the Environmental Manager to determine what is necessary | -----------------------------------------------------------------------------------------------------------------

## Pre-PS&E (85%)
PRELIMINARY PS&E SUBMISSION CHECKLIST
NOTE: THIS CHECKLIST IS EXPECTED TO BE MODIFIED AS THE STANDARDS FOR THE USE OF OPENROADS DESIGNER ARE DEVELOPED. USERS ARE ENCOURAGED TO CHECK THE NHDOT WEBSITE FOR AN UPDATED VERSION PRIOR TO USE.
[7 empty] | Version Date: | 2024-10-08 | Initials should be person who did the check.
PROJECT: | [8 empty] | The checker should be experienced.
ID |  | ITEM | NEW SINCE | DONE | DATE | CHECKED | DATE | REMARKS
|  |  | S&D SUB. | BY |  | BY
REQUIRED SUBMISSION ITEMS
Plans
Design Report
List of Anticipated Special Provisions for all items not available through the Department
Drainage Report
Quantity Calculations
REQUIRED DESIGN CHECKS
|  | Verify all comments from Slope and Drain Plan Submission have been addressed. | *
Vertical Curve vs. horizontal curve placement
K values vs. Green Book standards
Minimum/maximum grades vs. Green Book standards
Turning lanes and intersections designs per Design Manual sample layouts
Turn lanes, ramp lengths, etc. match traffic analysis
Turning movements at all side roads and commercial driveways
Intersection, passing, and stopping sight distances
Verify project begins and ends in a convenient and logical location
Verify property impacts are withing ROW or easements
Intersection and ramp nose grading (show contours developed by model)
Edge line profiles in superelevation transitions (show contours developed by model)
|  | Verify any drainage updates meet design guidelines noted on Slope and Drain Checklist | *
PREVIOUS CHECKLISTS REVIEWED
PLANS
|  | FRONT SHEET | *
|  | Location Map | *
|  | Project location designated with a circle and labeled with State Project Number | *
|  | North Arrow | *
|  | Major Roads Labeled | *
|  | Town, City, County & State names labeled and boundaries shown | *
|  | Rivers, brooks, streams, lakes, etc. labeled | *
|  | Railroads Labeled | *
|  | Graphic Scale | *
|  | Layout | *
|  | Show existing buildings (solid) roadway EP, drive EP's, bridges, railroads, and water bodies | *
|  | Label rivers, streams, brooks, lakes, roads, railroads, town/city, county & state boundaries. | *
|  | "To (Town or City)" at all ends of project with destination arrows | *
|  | North arrow (grid) | *
|  | Town/City of ( ) | *
|  | County of ( ) | *
|  | Scale | *
|  | Construction Approach notes | *
|  | Begin and End Construction with station | *
|  | Limit of Work with station | *
|  | Construction baseline with major stationing labeled | *
|  | Bridge Number labeled | *
|  | Miscellaneous | *
|  | Project name and (Federal & State) numbers | *
|  | Road name in sheet title | *
|  | Signature block(s) | *
|  | "Drafted by" and "Sheet Checked by" filled in | *
|  | Sheet numbers and project numbers | *
|  | Design data box completed in top left corner. | *
|  | INDEX OF SHEETS AND GENERAL NOTES | *
|  | Latest revision date verified | *
|  | Add general notes if required | *
|  | STANDARD SYMBOLS | *
|  | Latest revision date verified | *
TYPICAL SECTIONS
Appropriate item numbers and nomenclature
Aggregate base course material (Subgrade constants only for normal crown)
Underdrain
Special case typicals, i.e. side roads, curb details, etc.
Pavement types and depths, pavement joint treatment (if required), pavement unit/mass
Rock cuts consistent with Geotechnical Report
Slope roundings (Only shown on the typicals not on each cross section)
Superelevation treatment for shoulders (curbing treatment, if applicable)
Curb, guardrail offset, median condition
Maximum superelevation (E max)
General notes specific to the project
Drawn to scale (Note scale below each typical section)
|  | SUMMARY SHEETS | *
|  | Preliminary Roundings and Totals | *
|  | Completed Construction Notes (Drainage, etc.) | *
|  | Project stationing included in construction notes are to the whole number and offsets are to the tenth. | *
|  | Include the following Summary Tables as applicable: | *
|  | Drainage (Including Water Diversion Structures if Applicable) | *
|  | Curbing | *
|  | Tree Removal | *
|  | Loam & Sod Areas | *
|  | Pavement Markings (per road) | *
|  | Fencing | *
|  | Surfacing Materials (per road, drives etc.) | *
|  | Signalization, Lighting & Conduit | *
|  | Retaining Walls | *
|  | Guardrail and Concrete Barrier | *
|  | Sidewalk & Islands (if not self explanatory) | *
|  | Landscaping and Slope Protection | *
|  | Clearing and Grubbing | *
|  | Bounds | *
|  | Const. Signs and Warning Devices | *
|  | Earthwork | *
|  | Demolishing Buildings | *
Utilities by Type (If by Contractor)
|  | Force Account | *
|  | Materials to be Salvaged | *
|  | Work Done by Others | *
|  | Subsidiary Items | *
|  | Items consisting of subsidiary quantities (e.g.: Box Culvert, Temporary Widenings, etc.) | *
|  | All other items can be listed in Incidental Items | *
MISCELLANEOUS DETAIL SHEETS
Include details as needed (examples follow)
|  | Sidewalk ramps | [5 empty] | Available at Department website
|  | Driveway details | [5 empty] | Available at Department website
|  | Curved guardrail with CRT Posts | [5 empty] | Available at Department website
|  | Terminal Unit Delineation | [5 empty] | Available at Department website
|  | EAGRT Platforms | [5 empty] | Available at Department website
|  | Mid-Splice W-Beam guardrail stiffening | [5 empty] | Available at Department website
Pavement match detail
Special drainage ditch details
Stormwater BMPs
Slope protection
Retaining walls
Special catch basins
Permanent erosion control
Concrete islands
|  | Grading Plan (proposed elevations to 0.01 accuracy) | *
PLAN CUT SHEETS (add link to Sample Plans once created)
Detail listed below is a baseline for General Plans. Additional detail (indicated in the respective sections below) to consolidate plan sets may be shown as room allows. All detail shown to 0.1 accuracy unless otherwise noted.
Use engineering judgment if the precision is to be greater than noted.
GENERAL
North arrow (grid)
Existing detail (exclude miscellaneous text such as curb, sidewalk, and woods type, etc.)
Existing utilities
Use correct symbols for detail
Lettering must be legible when photographically reduced to 1/2 scale
Match lines to abutting sheets
Bench marks shown and described, if applicable
CAROW Access points addressed
Construction and Diversion Base line(s) labeled.
PC, PT shown, (curve data or PI’s not required)
Tree or bush annotations excluded
Extend existing detail and alignment beyond project limits
250 ft ± beyond project limits on 1:50 plans
150 ft ± beyond project limits for 1:20 plans
EP’s, TW’s, retaining walls, sidewalk
Wetlands delineated and identified by number through the Bureau of Environment
Invasive species areas delineated and identified by type through the Bureau of Environment
Monitoring well locations
Cross-hatch pavement removal outside slope lines
Cross-hatch structure removal with bold line style
Cross-hatch discontinued driveways outside of slope lines
PROPOSED PERMANENT LAYOUT AND DETAIL
Proposed work noted in upper case lettering
EP’s, TW’s, retaining walls, sidewalk
Curb without mark numbers
Guardrail and terminal units. (Guardrail notes are not required)
Slope lines and clearing lines
Clearing and grubbing areas shown and labeled.
Fences, pedestrian rail, and bike rail labeled
Signal mast arms (signal heads, pullboxes etc. not required)
Drainage (See Drainage Guidelines for more information)
Closed drainage system and culverts with flow arrows and drainage note callouts
Drive pipes shown
Stone protection
Erosion control treatment and/or water quality treatment shown and labeled, if appropriate
Proposed utilities
Overhead Sign Structures (sign text not required)
ROW
Parcel numbers and owner names as shown on abstracting plan
ROW type labeled similar to ROW Plans
Right-of-Way bounds shown
Fence LAROW with chain link or woven wire, as appropriate
All easements shown, including maintenance of detention basins, ditches, etc..
Easements labeled (do not shade or hatch)
NOTES
Road names (on each cut sheet)
No ROW notes (alignment radius, flagging etc.)
Limits of work and approach notes
Begin and End Project notes
Notes to “SAVE” or “SAVE IF POSSIBLE” or “Remove” trees, shrubs, etc. At or near slope lines, if questionable or resulting from Right-of-Way commitments.
Special construction notes (i.e. “REMOVE EXISTING PAVEMENT, PLACE HUMUS & SLOPE SEED”.)
Buildings to be demolished. If subject to prior removal, show date and cross hatch per ROW checklist
Projects with CAROW, note under the property owner’s name the number of access points granted. Even if it is zero. If the driveway will be constructed in the future, note the future location.
|  | Drainage notes | [5 empty] | Provide on separate sheet if needed
Quantity match lines (QML)
Graphic scale
PROFILES
Station and scale construction Base Line (same as on plan sheets)
Finish grade (bold line)
Original ground to nearest 0.1 foot and finish grade 0.01 foot
Rock line plotted
Normal high water labeled
Vertical curve data (including low points and high points)
Vertical curve information - VPI’s PVC’s, PVT’s, Curve Length, K Value
Grades, equations, bridges, rivers, and streams labeled
Profile datum
Show superelevation rates and transitions
Show proposed subgrade treatments including areas of extra sand
Begin and end of project notes
Limit of work and approach notes
Check profile elevations vs. cross-sections
Graphic scale
DRAINAGE AND UTILITY PLANS
North arrow (grid)
Include drainage notes on Drainage and Utility Plans, if space allows. The guidelines for writing drainage notes, see Appendix 13-10 Drainage Note Format. If these plans are too crowded, include the notes on a separate sheet placed prior to the first Drainage and Utility plan sheet.
Write drainage notes pre the standard guidelines
Existing ROW, (proposed) ROW, easements and property owners as noted on General Plans
Slope lines labeled
Construction Base Line(s) labeled (Diversion Base Line not required)
PC's and PT's shown but no curve data or PI's
Proposed TW’s, EP’s, drives curbing, retaining walls, sidewalk and guardrail (include existing guardrail, if it’s to remain in place). (Turning lane lines, stop bars, arrows etc. are not required.)
All drainage with flow arrows
Existing Drainage labeled
Wetlands delineated and identified by number
Streams, brooks, rivers, etc.
Stone inlet and outlet protection
Permanent erosion control shown and labeled
Existing Utilities (underground and aerial) with annotation
Existing utility poles flagged and labeled "R" (remove) only
Existing underground utilities shown and labeled (i.e., "to be abandoned in place", "to be removed", etc.)
Proposed Underground Utilities shown and labeled (i.e. “24” DIP Water, “8” Stl Gas”, “12” PVC Sewer”, etc.)
Proposed utility poles flagged (per symbol sheet)
Existing and proposed drainage and utilities
Pertinent existing detail
Beginning and end project notes, limit of work or ex. TW’s, EP’s, drives, sidewalks, etc. are not required
Existing and proposed signal mast arms or pedestals and lighting
(NOTE: Existing and proposed pullboxes, conduit, and control cabinets are not required but are always checked for conflicts)
Proposed overhead sign structures (sign text not required)
Road Names
Monitoring Wells
Graphic Scale
ALIGNMENT, CURBING, AND PAVEMENT LAYOUT PLANS
North arrow (grid)
Construction Base Line(s) labeled (Diversion Base Line not required)
Construction Base Line with equations (to 0.01 accuracy)
Bearings, curve data -- PC’s PT’s and PI’s (include PI coordinates) (to 0.01 accuracy)
Survey SDR traverse points with elevations (to 0.01 accuracy)
Begin and end taper notes (station, offset, and rate)
Roadway dimensions and drive widths
Drive radii shown and tangent point offsets at the roadway match labeled (to 0.01 accuracy)
All roadway intersection radius and tangential point offsets labeled
Proposed curb shown as heavy linestyle
Proposed EP’s, TW’s, lane lines, edge of sidewalk, and guardrail
Driveway notes
Curbing general notes, (required only on the first sheet of this series)
Existing TW’s, EP’s and driveways are not required
Road names
Match lines to abutting sheets
Graphic scale
PAVEMENT MARKING PLANS
North arrow (grid)
Construction Base Line(s) labeled (Diversion Base Line not required)
Construction Base Line with equations.
Begin and end taper notes (station, offset, and rate)
Proposed curb shown as heavy linestyle
Proposed EP’s, TW’s, lane lines, and edge of sidewalk
Lane usage, i.e., arrows, words
Crosswalk and stop bars
Pavement marking general notes, (required only on the first sheet of this series)
Existing TW’s, EP’s and driveways are not required
Road names
Match lines to abutting sheets
Graphic scale
SIGNAL PLANS
North arrow (grid)
Appropriate scale 1:20
Construction Base Line(s) labeled
Existing conduit, pullboxes, mast arms, controller cabinets, meter pedestals
Right-of-Way lines (as noted on the General Plans)
Proposed EP’s, TW’s, curbing, pavement markings, (arrows, crosswalks, stop bars, etc.). Specific line description, i. e., 4-inch SSL (w) not required
Underground utilities, and existing and proposed drainage
“Soil Borings” summary box and boring location with appropriate symbol
Proposed meter pedestal, controller cabinet, conduit and pull boxes for signals and lighting,
Proposed power source shown
Proposed mast arm lengths shown
Proposed vehicle detection shown (cameras, loops, detection zones, etc.)
Signal timing plan
Phasing diagram
Signal head diagrams
Traffic flow diagram with am/pm peak hours
Fire pre-emption system (if requested by the Town/City)
General notes
Road names
Graphic scale
|  | SIGNING AND LIGHTING PLANS (IF SEPARATE PLAN SECTION IS NEEDED | *
|  | North arrow (grid) | *
|  | Construction Base Line(s) labeled | *
|  | Existing utility poles (excluding data annotation), conduit and pullboxes | *
|  | Right-of-Way lines (as noted on the General Plans) | *
|  | Proposed EP's, TW's, drive curbing, lane lines, pavement marking (symbol or words) sidewalk, guardrail, and retaining walls | *
|  | Light pole bases, pullboxes, conduit, power source for lighting shown and labeled per reference notes) | *
Proposed Utility Poles
|  | Signs shown symbolically with correct designation, i.e. R1-1, per the MUTCD | *
|  | Guide signs showing the sign face/text, i.e. directional, route junctions, etc. are shown only on the traffic sign summary sheets (not the Signing Plans) | *
|  | Location of bridge mounted signs | *
|  | overhead signs & structures | *
|  | General notes | *
|  | Road names | *
|  | Graphic scale | *
TRAFFIC CONTROL PLANS
Narrative explaining TCP details should be included (this is typically shown on the first TCP sheet)
Existing detail (as noted on the general plans)
Proposed EP’s, TW’s, and drives as necessary
Temporary widenings, EP’s and/or TW’s
Existing and proposed drainage, including temporary drainage
Check constructability of drainage (i.e. 12 feet deep but 1 foot off TW).
Show proposed drainage constructed in previous phases
Check impacts that will occur when excavating to remove existing, or place new, drainage systems.
Concrete barrier, temporary guardrail, impact attenuators
Temporary widening shaded to differentiate from proposed work
Slope lines (temporary and proposed), label if unclear
Legend box , if necessary, with different shading to denote phased construction
Utilities (existing and proposed), as necessary
Delineated wetlands
Easements
Pavement markings with line descriptions (i. e., 4-inch SSL (w))
Temporary lighting with notes
Property owners names and parcel numbers
North arrow (grid)
Graphic scale
DIVERSION PLANS
Existing detail (as noted on the general plans)
Diversion and Construction Base line(s) labeled
Diversion Base Line with equations
Diversion bearings, curve data -- PC’s PT’s and PI’s (including PI coordinates)
Diversion EP’s and TW’s
Slope lines and clearing lines
Taper notes and offsets
Temporary signals (approximate locations)
Existing and proposed drainage, including temporary drainage
Show proposed drainage constructed in previous phases
Utilities (existing and proposed), as necessary
ROW and property lines (as noted on General plans)
Easements labeled (do not shade or hatch)
Parcel numbers and owner names (as noted on General Plans)
Drive notes
Match lines to abutting sheets
Radii labeled and offsets shown
Roadway dimensions
Concrete barrier, temporary guardrail, impact attenuators
Delineated Wetlands
North arrow (grid)
Graphic scale
|  | MITIGATION PLANS (if applicable) | *
|  | North arrow (grid) | *
|  | Road Names | *
|  | Property ROW lines with bounds | *
|  | Buildings, bridges, woods lines, trees, streams, brooks, rivers | *
|  | Fence Lines | *
|  | Slope lines and clearing lines labeled | *
|  | Boring or test pit location (shown by symbol) | *
|  | Monitoring well locations | *
|  | USFWS Wetland classifications | *
|  | Wetland delineation identified by number | *
|  | Base line layout for sectioning, if applicable | *
|  | Cross sections for quantity development (usually not included in roadway cross sections) | *
|  | Spot elevations, low points, high points | *
|  | Grading Plans, i.e., before and after contours. (use 0.5 - 1.0' contour intervals) | *
|  | Planting layout | *
|  | Special Provisions.Supplemental Specs (for the Proposal) | *
|  | Drainage inlet & outlet control details including elevations | *
|  | Typical section for proposed mitigation areas (depth of wetland humus, etc.) | *
|  | Proposed soils plan, including a seeding plan | *
|  | Clear labeling of proposed final water elevations | *
|  | Graphic Scale | *
CROSS SECTIONS
EXISTING DETAIL
Existing ground shown
TW’s, EP’s, curb, woods, center of road, guardrail, retaining wall, edge of river,
Stone walls, fences, and delineated wetland(s) labeled
| *ORD | Trees and poles with annotation and station (include lights on poles). Typically, only plot small and large trees per Spec. Book Label bushes (ornamental or special landscaping etc.) if at or near the slope lines and is to be saved.
| *ORD | CB’s, DI’s, manholes, etc. with station
| *ORD | Drainage pipes with size and flow arrow
Underground utilities shown on all sections. Describe the utility on the first section of the cut sheet
| *ORD | Houses and building sills with elevations
| *ORD | Signal, light pole, and sign foundations
MISCELLANEOUS LABELING
| *ORD | Pavement slopes 2%, 8%, of each lane and shoulder (including sidewalk)
Side Slopes 6:1, 4:1, varies etc.
| *ORD | Existing utility poles flagged and labeled "R" (remove) only
| *ORD | Existing underground utilities shown and labeled (i.e., "to be abandoned in place", "to be removed", etc.)
| *ORD | Lane and shoulder widths (May only label the first section on the cut sheet, unless in a taper)
Dimension grass panels, ditch offsets, etc. if not per typical
Drive dimensions at each break in slope along the drive and label the slope (%)
| *ORD | Existing drainage to be removed (label “REMOVE”)
Quantity match lines (QML)
Label offset from Construction Base Line to Diversion Base Line (Only needed if separate Diversion cross sections are not included)
| *ORD | Note trees that require special treatment, i.e., “SAVE, REMOVE, or SAVE, IF POSSIBLE”.
GENERAL
Plot rock and muck lines
Diversion “top line template” and bottom of aggregate base shown by dashed line.
Slope line “tick marks” reflect appropriate slope rounding
Transition embankment slopes correctly
Develop sections in rock areas @ +25 stationing
Existing ground elevations (tenth) and finish grade elevations (hundredth).
Roadway names and State project number
Guardrail areas, (include extended shoulder break and guardrail platforms)
Show stabilization of steep slopes (cut or fill) (stone slope protection or terracing)
Notes for “Begin and End Construction”, and “Limit of Work”
Proposed granite curb
Drives designed per Driveway Manual and detail sheet
DRAINAGE, UTILITIES, SIGN STRUCTURES, AND SIGNALS
Ditch elevations and flow arrows
| *ORD | Proposed drainage shown per symbol legend, drawn to correct offset and size
| *ORD | Labeled and referenced by flagging the note number at the CB or pipe
| *ORD | Outlet stone protection shown
| *ORD | Correct structure top shown (slab top or cone)
| *ORD | Granular backfill “box” for underdrain
| *ORD | Cross-pipe flow arrows
|  | Proposed signal, lighting, and sign foundations | *
|  | Proposed utility poled with flagging | *
|  | Proposed underground utilities shown with description on first section of cut sheet | *
DESIGN CHECKS
Cross section template matches the typical sections
Slope line “tick marks” match plan sheet slope lines
Verify Existing ground elevations and finish grade elevations match profile
Have required Geotechnical recommendations been shown
DETOUR SECTIONS
Provide same information as regular cross section
Temporary drainage (labeled similar to proposed)
Special notes
| *ORD | Typically, information shown back and ahead of stations is not required using OpenRoads, new standards are under development, coordinate with NHDOT PM on approach.

## PS&E - Const. Plans (95%-100%)
PS&E / CONSTRUCTION SUBMISSION CHECKLIST
NOTE: THIS CHECKLIST IS EXPECTED TO BE MODIFIED AS THE STANDARDS FOR THE USE OF OPENROADS DESIGNER ARE DEVELOPED. USERS ARE ENCOURAGED TO CHECK THE NHDOT WEBSITE FOR AN UPDATED VERSION PRIOR TO USE.
[7 empty] | Version Date: | 2024-10-08 | Initials should be person who did the check.
PROJECT: | [8 empty] | The checker should be experienced.
ID |  | ITEM | NEW SINCE | DONE | DATE | CHECKED | DATE | REMARKS
|  |  | PPS&E SUB. | BY |  | BY
REQUIRED SUBMISSION ITEMS
|  | Plans (Stamped by Engineer(s) of Record) | *
Design Report
|  | Finalized copies of Special Provisions for all items not available through the Department | *
|  | Drainage Report (Stamped by Engineer of Record) | *
Quantity Calculations
REQUIRED DESIGN CHECKS
Verify all comments from Preliminary PS&E Plan Submission have been addressed.
Vertical Curve vs. horizontal curve placement
K values vs. Green Book standards
Minimum/maximum grades vs. Green Book standards
Turning lanes and intersections designs per Design Manual sample layouts
Turn lanes, ramp lengths, etc. match traffic analysis
Turning movements at all side roads and commercial driveways
Intersection, passing, and stopping sight distances
Verify project begins and ends in a convenient and logical location
Verify property impacts are withing ROW or easements
Intersection and ramp nose grading (show contours developed by model)
Edge line profiles in superelevation transitions (show contours developed by model)
Verify any drainage updates meet design guidelines noted on Slope and Drain Checklist
PREVIOUS CHECKLISTS REVIEWED
PLANS
FRONT SHEET
Location Map
Project location designated with a circle and labeled with State Project Number
North Arrow
Major Roads Labeled
Town, City, County & State names labeled and boundaries shown
Rivers, brooks, streams, lakes, etc. labeled
Railroads Labeled
Graphic Scale
Layout
Show existing buildings (solid) roadway EP, drive EP's, bridges, railroads, and water bodies
Label rivers, streams, brooks, lakes, roads, railroads, town/city, county & state boundaries.
"To (Town or City)" at all ends of project with destination arrows
North arrow (grid)
Town/City of ( )
County of ( )
Scale
Construction Approach notes
Begin and End Construction with station
Limit of Work with station
Construction baseline with major stationing labeled
Bridge Number labeled
Miscellaneous
Project name and (Federal & State) numbers
Road name in sheet title
Signature block(s)
"Drafted by" and "Sheet Checked by" filled in
Sheet numbers and project numbers
Design data box completed in top left corner.
INDEX OF SHEETS AND GENERAL NOTES
Latest revision date verified
Add general notes if required
STANDARD SYMBOLS
Latest revision date verified
TYPICAL SECTIONS
Appropriate item numbers and nomenclature
Aggregate base course material (Subgrade constants only for normal crown)
Underdrain
Special case typicals, i.e. side roads, curb details, etc.
Pavement types and depths, pavement joint treatment (if required), pavement unit/mass
Rock cuts consistent with Geotechnical Report
Slope roundings (Only shown on the typicals not on each cross section)
Superelevation treatment for shoulders (curbing treatment, if applicable)
Curb, guardrail offset, median condition
Maximum superelevation (E max)
General notes specific to the project
Drawn to scale (Note scale below each typical section)
SUMMARY SHEETS
Completed Construction Notes (Drainage, etc.)
Project stationing included in construction notes are to the whole number and offsets are to the tenth.
Include the following Summary Tables as applicable:
Drainage (Including Water Diversion Structures if Applicable)
Curbing
Tree Removal
Loam & Sod Areas
Pavement Markings (per road)
Fencing
Surfacing Materials (per road, drives etc.)
Signalization, Lighting & Conduit
Retaining Walls
Guardrail and Concrete Barrier
Sidewalk & Islands (if not self explanatory)
Landscaping and Slope Protection
Clearing and Grubbing
Bounds
Const. Signs and Warning Devices
Earthwork
Demolishing Buildings
Force Account
Materials to be Salvaged
Utilities by Type (If by Contractor)
Work Done by Others
Subsidiary Items
Items consisting of subsidiary quantities (e.g.: Box Culvert, Temporary Widenings, etc.)
All other items can be listed in Incidental Items
|  | Tables should include quantity sums, with appropriate rounding | *
|  | Complete a "Three-way" check | *
|  | Complete "Apples & Oranges" Check. This compares summaries vs. estimates with item numbers and quantities totaled on each. Totals should be equal. | *
MISCELLANEOUS DETAIL SHEETS
Include details as needed (examples follow)
|  | Sidewalk ramps | [5 empty] | Available at Department website
|  | Driveway details | [5 empty] | Available at Department website
|  | Curved guardrail with CRT Posts | [5 empty] | Available at Department website
|  | Terminal Unit Delineation | [5 empty] | Available at Department website
|  | EAGRT Platforms | [5 empty] | Available at Department website
|  | Mid-Splice W-Beam guardrail stiffening | [5 empty] | Available at Department website
Pavement match detail
Special drainage ditch details
Stormwater BMPs
Slope protection
Retaining walls
Special catch basins
Permanent erosion control
Concrete islands
Grading Plan (proposed elevations to 0.01 accuracy)
PLAN CUT SHEETS (add link to Sample Plans once created)
Detail listed below is a baseline for General Plans. Additional detail (indicated in the respective sections below) to consolidate plan sets may be shown as room allows. All detail shown to 0.1 accuracy unless otherwise noted.
Use engineering judgment if the precision is to be greater than noted.
GENERAL
North arrow (grid)
Existing detail (exclude miscellaneous text such as curb, sidewalk, and woods type, etc.)
Existing utilities
Use correct symbols for detail
Lettering must be legible when photographically reduced to 1/2 scale
Match lines to abutting sheets
Bench marks shown and described, if applicable
CAROW Access points addressed
Construction and Diversion Base line(s) labeled.
PC, PT shown, (curve data or PI’s not required)
Tree or bush annotations excluded
Extend existing detail and alignment beyond project limits
250 ft ± beyond project limits on 1:50 plans
150 ft ± beyond project limits for 1:20 plans
EP’s, TW’s, retaining walls, sidewalk
Wetlands delineated and identified by number through the Bureau of Environment
Invasive species areas delineated and identified by type through the Bureau of Environment
Monitoring well locations
Cross-hatch pavement removal outside slope lines
Cross-hatch structure removal with bold line style
Cross-hatch discontinued driveways outside of slope lines
PROPOSED PERMANENT LAYOUT AND DETAIL
Proposed work noted in upper case lettering
EP’s, TW’s, retaining walls, sidewalk
Curb without mark numbers
Guardrail and terminal units. (Guardrail notes are not required)
Slope lines and clearing lines
Clearing and grubbing areas shown and labeled.
Fences, pedestrian rail, and bike rail labeled
Signal mast arms (signal heads, pullboxes etc. not required)
Drainage (See Drainage Guidelines for more information)
Closed drainage system and culverts with flow arrows and drainage note callouts
Drive pipes shown
Stone protection
Erosion control treatment and/or water quality treatment shown and labeled, if appropriate
Proposed utilities
Overhead Sign Structures (sign text not required)
ROW
Parcel numbers and owner names as shown on abstracting plan
ROW type labeled similar to ROW Plans
Right-of-Way bounds shown
Fence LAROW with chain link or woven wire, as appropriate
All easements shown, including maintenance of detention basins, ditches, etc..
Temporary slope easements not shown
Easements labeled (do not shade or hatch)
NOTES
Road names (on each cut sheet)
No ROW notes (alignment radius, flagging etc.)
Limits of work and approach notes
Begin and End Project notes
Notes to “SAVE” or “SAVE IF POSSIBLE” or “Remove” trees, shrubs, etc. At or near slope lines, if questionable or resulting from Right-of-Way commitments.
Special construction notes (i.e. “REMOVE EXISTING PAVEMENT, PLACE HUMUS & SLOPE SEED”.)
Buildings to be demolished. If subject to prior removal, show date and cross hatch per ROW checklist
Projects with CAROW, note under the property owner’s name the number of access points granted. Even if it is zero. If the driveway will be constructed in the future, note the future location.
|  | Drainage notes | [5 empty] | Provide on separate sheet if needed
Quantity match lines (QML)
Graphic scale
PROFILES
Station and scale construction Base Line (same as on plan sheets)
Finish grade (bold line)
Original ground to nearest 0.1 foot and finish grade 0.01 foot
Rock line plotted
Normal high water labeled
Vertical curve data (including low points and high points)
Vertical curve information - VPI’s PVC’s, PVT’s, Curve Length, K Value
Grades, equations, bridges, rivers, and streams labeled
Profile datum
Show superelevation rates and transitions
Show proposed subgrade treatments including areas of extra sand
Begin and end of project notes
Limit of work and approach notes
Check profile elevations vs. cross-sections
Graphic scale
DRAINAGE AND UTILITY PLANS
North arrow (grid)
Include drainage notes on Drainage and Utility Plans, if space allows. For guidelines for writing drainage notes, see Appendix 13-10 Drainage Note Format. If these plans are too crowded, include the notes on a separate sheet placed prior to the first Drainage and Utility plan sheet.
Write drainage notes per the standard guidelines
Existing ROW, (proposed) ROW, easements and property owners as noted on General Plans
Slope lines labeled
Construction Base Line(s) labeled (Diversion Base Line not required)
PC's and PT's shown but no curve data or PI's
Proposed TW’s, EP’s, drives curbing, retaining walls, sidewalk and guardrail (include existing guardrail, if it’s to remain in place). (Turning lane lines, stop bars, arrows etc. are not required.)
All drainage with flow arrows
Existing Drainage labeled
Wetlands delineated and identified by number
Streams, brooks, rivers, etc.
Stone inlet and outlet protection
Permanent erosion control shown and labeled
Existing Utilities (underground and aerial) with annotation
Existing utility poles flagged and labeled "R" (remove) only
Existing underground utilities shown and labeled (i.e., "to be abandoned in place", "to be removed", etc.)
Proposed utility poles flagged (per symbol sheet)
Proposed Underground Utilities shown and labeled (i.e. “24” DIP Water, “8” Stl Gas”, “12” PVC Sewer”, etc.)
Existing and proposed drainage and utilities
Pertinent existing detail
Beginning and end project notes, limit of work or ex. TW’s, EP’s, drives, sidewalks, etc. are not required
Existing and proposed signal mast arms or pedestals and lighting
(NOTE: Existing and proposed pullboxes, conduit, and control cabinets are not required but are always checked for conflicts)
Proposed overhead sign structures (sign text not required)
Road Names
Monitoring Wells
Graphic Scale
ALIGNMENT, CURBING, AND PAVEMENT LAYOUT PLANS
North arrow (grid)
Construction Base Line(s) labeled (Diversion Base Line not required)
Construction Base Line with equations (to 0.01 accuracy)
Bearings, curve data -- PC’s PT’s and PI’s (include PI coordinates) (to 0.01 accuracy)
Survey SDR traverse points with elevations (to 0.01 accuracy)
Begin and end taper notes (station, offset, and rate)
Roadway dimensions and drive widths
Drive radii shown and tangent point offsets at the roadway match labeled (to 0.01 accuracy)
All roadway intersection radius and tangential point offsets labeled
Proposed curb shown as heavy linestyle
Proposed EP’s, TW’s, lane lines, edge of sidewalk, and guardrail
Driveway notes
Curbing general notes, (required only on the first sheet of this series)
Existing TW’s, EP’s and driveways are not required
Road names
Match lines to abutting sheets
Graphic scale
PAVEMENT MARKING PLANS
North arrow (grid)
Construction Base Line(s) labeled (Diversion Base Line not required)
Construction Base Line with equations.
Begin and end taper notes (station, offset, and rate)
Proposed curb shown as heavy linestyle
Proposed EP’s, TW’s, lane lines, and edge of sidewalk
Lane usage, i.e., arrows, words
Crosswalk and stop bars
Pavement marking general notes, (required only on the first sheet of this series)
Existing TW’s, EP’s and driveways are not required
Road names
Station and offset for non-standard pavement markings (intersections, gores, etc.)
Signs (existing and proposed)
Match lines to abutting sheets
Graphic scale
SIGNAL PLANS
North arrow (grid)
Appropriate scale 1:20
Construction Base Line(s) labeled
Existing conduit, pullboxes, mast arms, controller cabinets, meter pedestals
Right-of-Way lines (as noted on the General Plans)
Proposed EP’s, TW’s, curbing, pavement markings, (arrows, crosswalks, stop bars, etc.). Specific line description, i. e., 4-inch SSL (w) not required
Underground utilities, and existing and proposed drainage
“Soil Borings” summary box and boring location with appropriate symbol
Proposed meter pedestal, controller cabinet, conduit and pull boxes for signals and lighting,
Proposed power source shown
Proposed mast arm lengths shown
Proposed vehicle detection shown (cameras, loops, detection zones, etc.)
Signal timing plan
Phasing diagram
Signal head diagrams
Traffic flow diagram with am/pm peak hours
Fire pre-emption system (if requested by the Town/City)
General notes
Road names
Graphic scale
SIGNING AND LIGHTING PLANS (IF SEPARATE PLAN SECTION IS NEEDED)
North arrow (grid)
Construction Base Line(s) labeled
Existing utility poles (excluding data annotation), conduit and pullboxes
Proposed Utility Poles
Right-of-Way lines (as noted on the General Plans)
Proposed EP's, TW's, drive curbing, lane lines, pavement marking (symbol or words) sidewalk, guardrail, and retaining walls
Light pole bases, pullboxes, conduit, power source for lighting shown and labeled per reference notes)
Signs shown symbolically with correct designation, i.e. R1-1, per the MUTCD
Guide signs showing the sign face/text, i.e. directional, route junctions, etc. are shown only on the traffic sign summary sheets (not the Signing Plans)
Existing signs flagged and labeled "REMOVE", "RELOCATE", or "RETAIN" (spell out entire word)
Location of bridge mounted signs
Overhead signs & structures
General notes
Road names
Graphic scale
TRAFFIC CONTROL PLANS
Narrative explaining TCP details should be included (this is typically shown on the first TCP sheet)
Existing detail (as noted on the general plans)
Proposed EP’s, TW’s, and drives as necessary
Temporary widenings, EP’s and/or TW’s
Existing and proposed drainage, including temporary drainage
Check constructability of drainage (i.e. 12 feet deep but 1 foot off TW).
Show proposed drainage constructed in previous phases
Check impacts that will occur when excavating to remove existing, or place new, drainage systems.
Concrete barrier, temporary guardrail, impact attenuators
Temporary widening shaded to differentiate from proposed work
Slope lines (temporary and proposed), label if unclear
Legend box , if necessary, with different shading to denote phased construction
Utilities (existing and proposed), as necessary
Delineated wetlands
Easements
Pavement markings with line descriptions (i. e., 4-inch SSL (w))
Temporary lighting with notes
Property owners names and parcel numbers
North arrow (grid)
Graphic scale
DIVERSION PLANS
Existing detail (as noted on the general plans)
Diversion and Construction Base line(s) labeled
Diversion Base Line with equations
Diversion bearings, curve data -- PC’s PT’s and PI’s (including PI coordinates)
Diversion EP’s and TW’s
Slope lines and clearing lines
Taper notes and offsets
Temporary signals (approximate locations)
Existing and proposed drainage, including temporary drainage
Show proposed drainage constructed in previous phases
Utilities (existing and proposed), as necessary
ROW and property lines (as noted on General plans)
Easements labeled (do not shade or hatch)
Parcel numbers and owner names (as noted on General Plans)
Drive notes
Match lines to abutting sheets
Radii labeled and offsets shown
Roadway dimensions
Concrete barrier, temporary guardrail, impact attenuators
Delineated Wetlands
North arrow (grid)
Graphic scale
MITIGATION PLANS (if applicable)
North arrow (grid)
Road Names
Property ROW lines with bounds
Buildings, bridges, woods lines, trees, streams, brooks, rivers
Fence Lines
Slope lines and clearing lines labeled
Boring or test pit location (shown by symbol)
Monitoring well locations
USFWS Wetland classifications
Wetland delineation identified by number
Base line layout for sectioning, if applicable
Cross sections for quantity development (usually not included in roadway cross sections)
Spot elevations, low points, high points
Grading Plans, i.e., before and after contours. (use 0.5 - 1.0' contour intervals)
Planting layout
Special Provisions.Supplemental Specs (for the Proposal)
Drainage inlet & outlet control details including elevations
Typical section for proposed mitigation areas (depth of wetland humus, etc.)
Proposed soils plan, including a seeding plan
Clear labeling of proposed final water elevations
Graphic Scale
CROSS SECTIONS (DISCUSS WHAT IS REQUIRED WITH NHDOT PROJECT PM)
EXISTING DETAIL
Existing ground shown
TW’s, EP’s, curb, woods, center of road, guardrail, retaining wall, edge of river,
Stone walls, fences, and delineated wetland(s) labeled
| *ORD | Trees and poles with annotation and station (include lights on poles). Typically, only plot small and large trees per Spec. Book Label bushes (ornamental or special landscaping etc.) if at or near the slope lines and is to be saved.
| *ORD | CB’s, DI’s, manholes, etc. with station
| *ORD | Drainage pipes with size and flow arrow
| *ORD | Underground utilities shown on all sections. Describe the utility on the first section of the cut sheet
| *ORD | Houses and building sills with elevations
| *ORD | Signal, light pole, and sign foundations
MISCELLANEOUS LABELING
| *ORD | Pavement slopes 2%, 8%, of each lane and shoulder (including sidewalk)
Side Slopes 6:1, 4:1, varies etc.
| *ORD | Existing utility poles flagged and labeled "R" (remove) only
| *ORD | Existing underground utilities shown and labeled (i.e., "to be abandoned in place", "to be removed", etc.)
| *ORD | Lane and shoulder widths (May only label the first section on the cut sheet, unless in a taper)
Dimension grass panels, ditch offsets, etc. if not per typical
Drive dimensions at each break in slope along the drive and label the slope (%)
| *ORD | Existing drainage to be removed (label “REMOVE”)
Quantity match lines (QML)
Label offset from Construction Base Line to Diversion Base Line (Only needed if separate Diversion cross sections are not included)
| *ORD | Note trees that require specific treatment, i.e., “SAVE, REMOVE, or SAVE, IF POSSIBLE”.
GENERAL
Plot rock and muck lines
Diversion “top line template” and bottom of aggregate base shown by dashed line.
Slope line “tick marks” reflect appropriate slope rounding
Transition embankment slopes correctly
Develop sections in rock areas @ +25 stationing
Existing ground elevations (tenth) and finish grade elevations (hundredth).
Roadway names and State project number
Guardrail areas, (include extended shoulder break and guardrail platforms)
Show stabilization of steep slopes (cut or fill) (stone slope protection or terracing)
Notes for “Begin and End Construction”, and “Limit of Work”
Proposed granite curb
Drives designed per Driveway Manual and detail sheet
|  | Enter excavation quantities per sheet | *
DRAINAGE, UTILITIES, SIGN STRUCTURES, AND SIGNALS
Ditch elevations and flow arrows
| *ORD | Proposed drainage shown per symbol legend, drawn to correct offset and size
| *ORD | Labeled and referenced by flagging the note number at the CB or pipe
| *ORD | Outlet stone protection shown
| *ORD | Correct structure top shown (slab top or cone)
| *ORD | Granular backfill “box” for underdrain
| *ORD | Cross-pipe flow arrows
Proposed signal, lighting, and sign foundations
Proposed utility poled with flagging
Proposed underground utilities shown with description on first section of cut sheet
DESIGN CHECKS
Cross section template matches the typical sections
Slope line “tick marks” match plan sheet slope lines
Verify Existing ground elevations and finish grade elevations match profile
Have required Geotechnical recommendations been shown
DETOUR SECTIONS
Provide same information as regular cross section
Temporary drainage (labeled similar to proposed)
Special notes
| *ORD | Typically, information shown back and ahead of stations is not required using OpenRoads, new standards are under development, coordinate with NHDOT PM on approach.